## Tool Decisions
Tool decisions — what we use and why
Prepared 9 Oct 2026 · Pathways Technologies for NKG East Africa
Layer | Tool | Why | When we would change
Operational data store | Dataverse | The apps, flows, approvals, audit and security all need a transactional store. Dataverse gives alternate keys (no duplicates), field security, audit and business process flows out of the box. | Not expected to change.
Data intake (now) | Email → SharePoint → Power Query dataflow → Dataverse | No API access to XBS or Comtras today. Scheduled report emails are fully automatic once the senders are scheduled, and need no IT integration. | Swap to API/gateway per source when NKG grants access (C12, C13).
Data intake (target) | Custom connector (REST API) or on-premises data gateway (SQL view) | Removes the email dependency and gives near real-time data. | When XBS/Comtras API or read-only DB access is approved.
Reconciliation engine | Power Query dataflows + Power Automate on Dataverse | Volumes (~1,000 outturns, ~50k lines per snapshot) fit comfortably; one platform to support. | Move to a Fabric notebook only if the performance test (MO-13) misses the 30-minute target.
Microsoft Fabric | Optional, phase 2 | Not required to deliver zero-variance reconciliation. Useful for long history, trends and Direct Lake reporting if NKG already has Fabric capacity. | Confirm whether NKG has a Fabric capacity (F-SKU); if yes, enable Dataverse Link to Fabric after go-live.
Apps | Power Apps canvas (Stock Take app, Hub) + model-driven (Control Centre) | Canvas for mobile counting and operational screens; model-driven for finance-grade forms, views, BPFs and audit. | —
Automation | Power Automate cloud flows | Native to Dataverse, Outlook, SharePoint, Teams and Approvals; owned by service account. | —
Reporting | Power BI (Dataverse connector, PBIP in Git) | Standard NKG reporting tool; RLS; embedded in Control Centre. | Direct Lake if Fabric is adopted.
AI assistant | Copilot Studio | Read-only assistant in Teams and the Control Centre, answers from Dataverse with the user's own permissions. | Depends on Copilot approval/licensing (OD8); fallback = search and views.
ALM | Solutions, pac CLI, pipelines, Git | Repeatable deployments DEV → UAT → PROD; no dependency on any personal account. | —
Discipline colours
Power Apps
Power Automate
UI
UX
Data Engineering
Data Analyst
Copilot
Architecture / ALM
Testing / QA

## Development Tasks
Stocktake Optimization — Development Task Matrix
Every build task, the discipline it belongs to, the tool used and how it connects. Red = to confirm with NKG. Plan ID links to STOCKTAKE_Team_Work_Plan.xlsx.
Dev ID | Module | Development task | What is built | Discipline | Tool / platform | How (integration method) | Now vs target | Owner | Work-plan ID | Start | End | Work days | Licence needed | Status
A01 | Foundation | Set up DEV / UAT / PROD environments with Dataverse | Three environments, Dataverse database, region, admins | Architecture / ALM | Power Platform Admin Center | Admin centre configuration (manual, scripted later with pac admin) | Now | Moses Masibo | MO-03 | 2026-10-12 | 2026-10-16 | 5 | Power Apps/Automate Premium | Not started
A02 | Foundation | DLP policy | Business group: Dataverse, SharePoint, Outlook, Teams, Approvals, Power BI, Copilot Studio; block consumer connectors | Architecture / ALM | Power Platform Admin Center | Tenant/environment DLP policy | Now | Moses Masibo | MO-03 | 2026-10-12 | 2026-10-16 | 5 | Standard M365 | Not started
A03 | Foundation | Publisher (prefix stk) and 4 solutions | STK Core, STK Apps, STK Automation, STK Copilot | Architecture / ALM | Power Apps maker portal (Solutions) | Solution framework | Now | Moses Masibo | MO-04 | 2026-10-14 | 2026-10-15 | 2 | Power Apps/Automate Premium | Not started
A04 | Foundation | Environment variables and connection references | Mailbox, SharePoint URL, thresholds, Teams channel; one connection reference per connector | Architecture / ALM | Dataverse solution components | Deployment settings JSON per environment | Now | Moses Masibo | MO-04 | 2026-10-15 | 2026-10-16 | 2 | Power Apps/Automate Premium | Not started
A05 | Foundation | Service account stk.svc | Owns all flows/connections; licensed; MFA exception for automation | Architecture / ALM | Entra ID + M365 admin | Admin set-up by NKG IT | Now | Moses Masibo | PM-16 | 2026-10-12 | 2026-10-16 | 5 | Power Apps/Automate Premium | Not started
A06 | Foundation | Git repository and branching | /solutions /powerbi /docs /test /legacy; main/develop/feature; PR review | Architecture / ALM | Azure DevOps or GitHub — confirm | Git + pac solution unpack | Now | Moses Masibo | MO-05 | 2026-10-13 | 2026-10-15 | 3 | Standard M365 | Not started
A07 | Foundation | Build and release pipeline | Export → unpack → commit → managed build → deploy UAT/PROD | Architecture / ALM | Power Platform Pipelines / pac CLI in DevOps | pac CLI + Power Platform Build Tools | Now | Moses Masibo | MO-09 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
A08 | Foundation | Security roles and Entra groups | 10 roles, SG-STK-<Role> groups mapped to Dataverse teams | Architecture / ALM | Dataverse security + Entra ID | Group teams (Entra group sync) | Now | Moses Masibo | MO-08 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
A09 | Foundation | Field-level security and auditing | Hide expected qty from counters; protect approvals/config; audit on all stk_ tables | Architecture / ALM | Dataverse | Field security profiles + audit settings | Now | Moses Masibo | MO-08 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
A10 | Foundation | Take over ITB solution | Export managed solution, transfer flow/app ownership to stk.svc, store in Git /legacy | Architecture / ALM | Power Platform Admin Center | Admin ownership change + solution export | Now | Moses Masibo | MO-01, MO-02 | 2026-10-12 | 2026-10-14 | 3 | Power Apps/Automate Premium | Not started
A11 | Foundation | Health monitoring and housekeeping (F40, F41) | Hourly flow health check; weekly archive and purge | Power Automate | Power Automate cloud flows | Power Platform for Admins connector + Dataverse connector | Now | Moses Masibo | MO-11 | 2026-11-02 | 2026-11-04 | 3 | Power Apps/Automate Premium | Not started
B01 | Data model | Reference tables | stk_warehouse, location, zone, grade, qualitycode, packingtype, config | Data Engineering | Dataverse | Table design in solution | Now | Denis Otieno | DO-03 | 2026-10-15 | 2026-10-21 | 4 | Power Apps/Automate Premium | Not started
B02 | Data model | Basket and contract tables | stk_secondarybasket, primarybasket, contract (with lineage), mapping (versioned, effective dates) | Data Engineering | Dataverse | Table design + alternate keys | Now | Denis Otieno | DO-03 | 2026-10-15 | 2026-10-21 | 4 | Power Apps/Automate Premium | Not started
B03 | Data model | Snapshot and source-line tables | stk_snapshot, xbsline, comtrasline, movement, loadlog | Data Engineering | Dataverse | Table design; alternate key = snapshot + source row key | Now | Denis Otieno | DO-03 | 2026-10-15 | 2026-10-21 | 4 | Power Apps/Automate Premium | Not started
B04 | Data model | Count tables | stk_stocktake, assignment, countline (alt key stk_localid), recount | Data Engineering | Dataverse | Table design; idempotent alternate key for offline sync | Now | Denis Otieno | DO-03 | 2026-10-15 | 2026-10-21 | 4 | Power Apps/Automate Premium | Not started
B05 | Data model | Reconciliation tables | stk_reconrun, reconline, reconitem, period, signoff | Data Engineering | Dataverse | Table design | Now | Denis Otieno | DO-03 | 2026-10-15 | 2026-10-21 | 4 | Power Apps/Automate Premium | Not started
B06 | Data model | Exception and control tables | stk_exception (alt key rule+key), comment, correction, provisional, register, registermove, thirdpartyconf, feedback | Data Engineering | Dataverse | Table design | Now | Denis Otieno | DO-03 | 2026-10-15 | 2026-10-21 | 4 | Power Apps/Automate Premium | Not started
B07 | Data model | Optional: long-term history store | 24+ months of snapshots and recon lines for trend analysis | Data Engineering | Microsoft Fabric Lakehouse (optional) | Dataverse "Link to Microsoft Fabric" (no-copy shortcut) — only if NKG has Fabric capacity | Target (phase 2) | Denis Otieno | — | 2026-12-14 | 2027-01-15 | 25 | Fabric capacity (F-SKU) — confirm NKG has it | Not started
C01 | Data intake | Shared mailbox and SharePoint STK-Intake site | Mailbox stocktake.data@nkg.coffee; libraries Incoming / Rejected / Processed / Templates | Data Engineering | Exchange Online + SharePoint Online | Admin set-up by NKG IT | Now | Moses Masibo | MO-07 | 2026-10-15 | 2026-10-16 | 2 | Standard M365 | Not started
C02 | Data intake | F01 Receive intake email | Parse subject STK¦SOURCE¦DATE¦TIME; sender allow-list; save attachment with standard name | Power Automate | Power Automate cloud flow | Office 365 Outlook connector (shared mailbox trigger) + SharePoint connector | Now (email file intake) | Denis Otieno | DO-04 | 2026-10-19 | 2026-10-21 | 2 | Standard M365 | Not started
C03 | Data intake | F02 Validate file (V1–V7) | Columns, types, dates, row counts, duplicates, control totals, period; reject with reason | Power Automate | Power Automate + Office Scripts / Excel Online | Excel Online (Business) connector "List rows"/Office Script; SharePoint move file; Outlook reply | Now | Denis Otieno | DO-05 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
C04 | Data intake | Dataflow: XBS stock on hand | Load XBS stock file to stk_xbsline with snapshot id | Data Engineering | Power Query dataflow (Power Platform) → Dataverse | SharePoint folder source → Dataverse table (upsert on alt key) | Now (file) → Target: XBS API/DB view | Denis Otieno | DO-06 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
C05 | Data intake | Dataflow: XBS movements | Receipts, issues, transfers, processing, adjustments to stk_movement | Data Engineering | Power Query dataflow → Dataverse | SharePoint folder source | Now (file) → Target: XBS API | Denis Otieno | DO-06 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
C06 | Data intake | Dataflow: Comtras/BRIC 526 inventory | Basket/contract/lot balances to stk_comtrasline | Data Engineering | Power Query dataflow → Dataverse | SharePoint folder source | Now (file) → Target: Comtras API / SQL read-only view | Denis Otieno | DO-06 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
C07 | Data intake | Dataflow: Comtras/BRIC 537 sales relief | Sale relief by basket/lot | Data Engineering | Power Query dataflow → Dataverse | SharePoint folder source | Now (file) → Target: Comtras API | Denis Otieno | DO-06 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
C08 | Data intake | Dataflow: contracts, SNI, provisional, third-party balances | Contracts with amendments; stuffed-not-invoiced; direct-purchase pipeline; third-party statements | Data Engineering | Power Query dataflow → Dataverse | SharePoint folder source (Excel templates) | Now (file) | Denis Otieno | DO-06 | 2026-10-19 | 2026-10-23 | 4 | Power Apps/Automate Premium | Not started
C09 | Data intake | F03 Load orchestration | Trigger dataflow refresh, poll status, write snapshot header, compare row count to file | Power Automate | Power Automate cloud flow | Dataflows connector (Refresh a dataflow) + Dataverse connector | Now | Denis Otieno | DO-06 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
C10 | Data intake | F04 Missing feed, F05 Reprocess, F06 Lock snapshot | EX20 at 08:00; Hub reprocess button; lock month-end snapshot | Power Automate | Power Automate cloud flows | Recurrence + Dataverse connector; Power Apps (V2) trigger | Now | Denis Otieno | DO-08 | 2026-10-26 | 2026-10-27 | 2 | Power Apps/Automate Premium | Not started
C11 | Data intake | Manual upload fallback | Hub screen uploads file into Incoming so the same validation runs | Power Apps | Power Apps canvas (Hub) | Attachment control → flow → SharePoint create file | Now | Andrew Tanui | AN-10 | 2026-11-05 | 2026-11-06 | 2 | Power Apps/Automate Premium | Not started
C12 | Data intake | XBS API custom connector | Replace email intake for XBS when API/DB access is granted; downstream unchanged | Data Engineering | Power Platform custom connector (or on-premises data gateway) | REST API (OpenAPI definition) or SQL via on-premises data gateway | Target (when NKG grants API access) | Denis Otieno | — | TBC | TBC |  | Power Apps/Automate Premium | Not started
C13 | Data intake | Comtras/BRIC API custom connector | Same as C12 for 526/537/contracts | Data Engineering | Power Platform custom connector / gateway | REST API or SQL read-only view via gateway | Target (when NKG grants API access) | Denis Otieno | — | TBC | TBC |  | Power Apps/Automate Premium | Not started
C14 | Data intake | Optional: Fabric ingestion pipeline | If volumes grow: Data Factory pipeline lands files/API data in Lakehouse, Dataflow Gen2 writes curated tables | Data Engineering | Microsoft Fabric (Data Factory, Dataflow Gen2) | Pipeline copy activity / REST / SQL connector | Target (phase 2, optional) | Denis Otieno | — | TBC | TBC |  | Fabric capacity (F-SKU) — confirm NKG has it | Not started
D01 | Master data | Migrate reference data from ITB SharePoint lists | Warehouses, locations, grades, packing types | Data Engineering | Power Query dataflow → Dataverse | SharePoint list connector (one-off load) | Now | Denis Otieno | DO-07 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
D02 | Master data | Load baskets, contracts and mappings | Secondary → primary baskets; outturn → grade → basket mapping | Data Engineering | Power Query dataflow → Dataverse | Excel extracts from Comtras (file) → dataflow | Now | Denis Otieno | DO-07 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
D03 | Master data | Mapping coverage analysis | Unmapped/conflicting outturns with eq60 impact for Trade/QC | Data Analyst | Power BI Desktop / Excel | Dataverse connector (Power Query) | Now | Nicole Akinyi | NI-02 | 2026-10-15 | 2026-10-21 | 4 | Power BI Pro | Not started
D04 | Master data | Data profiling of sample files | Row counts, keys, duplicates, blanks, codes vs templates | Data Analyst | Power Query / Excel (or Fabric notebook if available) | File-based profiling | Now | Nicole Akinyi | NI-01 | 2026-10-13 | 2026-10-16 | 4 | Standard M365 | Not started
E01 | Engine | Normalisation (units, kg, eq60) | Apply unit rules and packing nominal kg to every position | Data Engineering | Power Query dataflow → Dataverse | Computed columns in dataflow (one rule set) | Now | Denis Otieno | DO-09 | 2026-10-26 | 2026-10-28 | 3 | Power Apps/Automate Premium | Not started
E02 | Engine | Mass balance | Opening + receipts − issues ± adjustments = closing per outturn | Data Engineering | Power Query dataflow → Dataverse | Group/merge in dataflow; results to stk_reconline | Now | Denis Otieno | DO-09 | 2026-10-26 | 2026-10-28 | 3 | Power Apps/Automate Premium | Not started
E03 | Engine | L1 Physical vs XBS | Count vs locked snapshot; attach reconciling items in fixed order; EX01/EX02 | Data Engineering | Dataflow + Power Automate (F30) | Dataverse connector; child flows per RI rule | Now | Denis Otieno | DO-10 | 2026-10-27 | 2026-10-29 | 3 | Power Apps/Automate Premium | Not started
E04 | Engine | L2 XBS vs Comtras | SNI add-back, provisional, registers; RI DOWNGRADE, WRONG-BASKET, ROLLOVER etc.; EX15 | Data Engineering | Dataflow + Power Automate | Dataverse connector | Now | Denis Otieno | DO-11 | 2026-10-29 | 2026-11-03 | 4 | Power Apps/Automate Premium | Not started
E05 | Engine | L3 Baskets vs Contracts | Basket balances vs contract open qty with lineage | Data Engineering | Dataflow + Power Automate | Dataverse connector | Now | Denis Otieno | DO-12 | 2026-11-02 | 2026-11-04 | 3 | Power Apps/Automate Premium | Not started
E06 | Engine | Residual calculation and run log | Residual = raw − Σ RI − Σ posted corrections; stk_reconrun header | Data Engineering | Dataverse (rollup/calculated) + flow | Dataverse Web API via connector | Now | Denis Otieno | DO-10 | 2026-10-27 | 2026-10-29 | 3 | Power Apps/Automate Premium | Not started
E07 | Engine | Optional: engine in Fabric notebook | If Dataverse/flow run time exceeds NFR-02 at full volume, move L1–L3 to a PySpark/SQL notebook writing back to Dataverse | Data Engineering | Microsoft Fabric notebook (optional) | Link to Fabric + Dataverse Web API write-back | Fallback only if performance test fails | Denis Otieno | MO-13 | TBC | TBC |  | Fabric capacity (F-SKU) — confirm NKG has it | Not started
F01 | Rules | F20 Daily rules run EX05–EX20 | Mass balance and rule checks at 08:15 | Power Automate | Power Automate cloud flow | Recurrence trigger + Dataverse connector + child flows | Now | Denis Otieno | DO-13 | 2026-10-28 | 2026-11-04 | 6 | Power Apps/Automate Premium | Not started
F02 | Rules | Exception upsert child flow | Upsert on alternate key rule+key; auto-close when cleared | Power Automate | Power Automate child flow | Dataverse "Upsert a row" (alternate key) | Now | Denis Otieno | DO-13 | 2026-10-28 | 2026-11-04 | 6 | Power Apps/Automate Premium | Not started
F03 | Rules | F21 Exception notifications and escalation | Owner alerts, 16:00 reminders, escalate after SLA × 2 | Power Automate | Power Automate cloud flow | Teams connector (adaptive card) + Outlook connector | Now | Jones Alukwe | JO-05 | 2026-10-27 | 2026-10-29 | 3 | Standard M365 | Not started
F04 | Rules | F23 Provisional auto-match; F28 correction posting check | Close provisional on XBS receipt; confirm corrections from next snapshot / EX13 | Power Automate | Power Automate cloud flows | Dataverse "When a row is added" trigger | Now | Denis Otieno | DO-14 | 2026-11-03 | 2026-11-05 | 3 | Power Apps/Automate Premium | Not started
G01 | UX | User personas and journeys | Counter, supervisor, Ops admin, Trade, QC, Logistics, Finance, Management — tasks and pain points from discovery | UX | Figma / PowerPoint | Workshop output from discovery recordings | Now | William Imo | PM-13 | 2026-10-12 | 2026-10-13 | 2 | Standard M365 | Not started
G02 | UX | Wireframes and clickable prototype | Based on the 10 mockups; refine after NKG walkthrough | UX | Figma (or Power Apps prototype) | Design review with NKG | Now | William Imo | PM-13 | 2026-10-12 | 2026-10-14 | 3 | Standard M365 | Not started
G03 | UX | Count journey design (blind count, found-elsewhere, offline) | One location at a time; 3 taps per line target; error states | UX | Figma | Usability walk-through with 2 counters on the floor | Now | William Imo | WI-05 | 2026-10-14 | 2026-10-16 | 3 | Standard M365 | Not started
G04 | UX | Reconciliation workspace journey | Summary-first, drill-down, side panel evidence; residual always visible | UX | Figma | Review with Finance | Now | Jones Alukwe | JO-06 | 2026-10-26 | 2026-10-27 | 2 | Standard M365 | Not started
G05 | UX | Usability tests | Counters (phone, gloves, far zones), supervisors, Finance; SUS score ≥ 70 | UX | Power Apps (UAT build) | Moderated test sessions | Now | Frankie Omasaja | WI-10 | 2026-11-03 | 2026-11-05 | 3 | Standard M365 | Not started
G06 | UX | Accessibility review | Font ≥ 16 pt, contrast, colour not only signal, 44 px targets | UX | Power Apps Accessibility checker | App checker + manual review | Now | William Imo | WI-10 | 2026-11-04 | 2026-11-05 | 2 | Standard M365 | Not started
H01 | UI | NKG theme and component library | Colours (#006330, #69ac45, teal, yellow, red, orange), header, buttons, chips, tiles, inputs | UI | Power Apps component library | Shared component library imported into each canvas app | Now | William Imo | WI-02 | 2026-10-13 | 2026-10-14 | 2 | Power Apps/Automate Premium | Not started
H02 | UI | Icon set and status chips | Closed / in progress / not started / recount / elsewhere / unidentified | UI | Power Apps (SVG icons) | Inline SVG in components | Now | Andrew Tanui | WI-02 | 2026-10-13 | 2026-10-14 | 2 | Power Apps/Automate Premium | Not started
H03 | UI | Model-driven app theme | NKG header colour/logo; form layouts; view columns | UI | Power Apps model-driven (modern theme) | App theme XML / modern theming | Now | Jones Alukwe | JO-02 | 2026-10-15 | 2026-10-19 | 3 | Power Apps/Automate Premium | Not started
H04 | UI | Responsive layouts | Phone portrait for Stock Take app; desktop 1366+ for Hub; tablet check | UI | Power Apps canvas | Responsive containers | Now | William Imo | WI-03 | 2026-10-15 | 2026-10-16 | 2 | Power Apps/Automate Premium | Not started
H05 | UI | QR location label design | A01–G14 labels with code, zone, warehouse, QR | UI | Word template + Power Automate | Word Online (Business) "Populate a template" → PDF | Now | Andrew Tanui | AN-03 | 2026-10-21 | 2026-10-22 | 2 | Power Apps/Automate Premium | Not started
I01 | Stock Take app | S1 Sign-in, version check, S2 Home | SSO, role and warehouse; App.MinVersion; tiles and countdown banner | Power Apps | Power Apps canvas (mobile) | Dataverse connector | Now | William Imo | WI-03 | 2026-10-15 | 2026-10-16 | 2 | Power Apps/Automate Premium | Not started
I02 | Stock Take app | S3 My Assignments | Locations by zone with status; search | Power Apps | Power Apps canvas | Dataverse (delegable Filter) | Now | William Imo | WI-04 | 2026-10-19 | 2026-10-22 | 3 | Power Apps/Automate Premium | Not started
I03 | Stock Take app | S4 Location with QR scan | Scan bay label or pick; start / mark empty / cannot access | Power Apps | Power Apps canvas | Barcode reader control | Now | William Imo | WI-04 | 2026-10-19 | 2026-10-22 | 3 | Power Apps/Automate Premium | Not started
I04 | Stock Take app | S5 Capture | Outturn scan/search, line types, grade from mapping, packing default, bags + pocket, live units/kg/eq60, category, photo | Power Apps | Power Apps canvas | Barcode reader + camera control + Dataverse | Now | William Imo | WI-05 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
I05 | Stock Take app | S6 Location summary and close | Totals, edit, close location | Power Apps | Power Apps canvas | ForAll + Patch to Dataverse | Now | William Imo | WI-06 | 2026-10-26 | 2026-10-27 | 2 | Power Apps/Automate Premium | Not started
I06 | Stock Take app | Offline queue and sync (S9) | SaveData/LoadData queue, timer sync, failed state, idempotent | Power Apps | Power Apps canvas | SaveData/LoadData + Dataverse upsert on stk_localid | Now | William Imo | WI-07 | 2026-10-27 | 2026-10-29 | 3 | Power Apps/Automate Premium | Not started
I07 | Stock Take app | Smart warnings | Duplicate, counted elsewhere, implausible qty, pocket ≥ bag, closed location | Power Apps | Power Apps canvas | Power Fx validation | Now | William Imo | WI-08 | 2026-10-28 | 2026-10-30 | 3 | Power Apps/Automate Premium | Not started
I08 | Stock Take app | S7 Recount, S8 100% issue/receive, S10 Help | Double-blind recount; movement during count; help + Copilot link | Power Apps | Power Apps canvas | Dataverse connector; Copilot deep link | Now | William Imo | WI-09 | 2026-10-29 | 2026-11-02 | 3 | Power Apps/Automate Premium | Not started
I09 | Stock Take app | F11 Bulk submit; F12 Not-in-list alert | Batch upsert >50 lines; supervisor alert with photo | Power Automate | Power Automate cloud flows | Power Apps (V2) trigger; Dataverse upsert; Teams adaptive card | Now | William Imo | WI-06, WI-08 | 2026-10-26 | 2026-10-30 | 5 | Power Apps/Automate Premium | Not started
J01 | Hub | Admin screens | Warehouses, grades, packing, unit rules, config editor, users | Power Apps | Power Apps canvas (desktop) | Dataverse connector | Now | Andrew Tanui | AN-02 | 2026-10-15 | 2026-10-19 | 3 | Power Apps/Automate Premium | Not started
J02 | Hub | Location generator + QR labels | Generate A01–G14; print labels | Power Apps | Power Apps canvas + Power Automate | Dataverse + Word template flow | Now | Andrew Tanui | AN-03 | 2026-10-21 | 2026-10-22 | 2 | Power Apps/Automate Premium | Not started
J03 | Hub | Stock take wizard + F10 notify | 5 steps with pre-checks; creates stock take, assignments, hidden expected lines; notifies counters | Power Apps | Power Apps canvas + Power Automate | Dataverse; Teams adaptive card + Outlook | Now | Andrew Tanui | AN-04 | 2026-10-21 | 2026-10-26 | 4 | Power Apps/Automate Premium | Not started
J04 | Hub | Assignments board | Assign by zone; auto-balance; block self-recount | Power Apps | Power Apps canvas | Dataverse connector | Now | Andrew Tanui | AN-05 | 2026-10-26 | 2026-10-27 | 2 | Power Apps/Automate Premium | Not started
J05 | Hub | Live monitor | KPIs, floor map, counter progress, uncounted, counted-not-in-XBS; 60-s refresh | Power Apps | Power Apps canvas | Dataverse (Timer + Refresh) | Now | Andrew Tanui | AN-06 | 2026-10-27 | 2026-10-29 | 3 | Power Apps/Automate Premium | Not started
J06 | Hub | F13 Location variance check + recount/unidentified queues | Hidden expected vs counted; recount to different counter | Power Automate | Power Automate + Power Apps | Dataverse "When a row is modified" trigger | Now | Andrew Tanui | AN-07 | 2026-10-29 | 2026-10-30 | 2 | Power Apps/Automate Premium | Not started
J07 | Hub | Variance review, approvals, close count + F14 | Supervisor actions with comment; close triggers L1 | Power Apps | Power Apps canvas + Power Automate | Dataverse trigger → F30 child flow | Now | Andrew Tanui | AN-08 | 2026-11-02 | 2026-11-03 | 2 | Power Apps/Automate Premium | Not started
J08 | Hub | Third-party confirmations + F15 | Statements M−5, chase M−3, escalate M−2 | Power Automate | Power Automate + Power Apps | Outlook connector (send/receive) + Dataverse | Now | Andrew Tanui | AN-09 | 2026-11-04 | 2026-11-05 | 2 | Power Apps/Automate Premium | Not started
J09 | Hub | Registers + F24, imports log, audit screen | Disputed, franchise, ex-office, sweepings, loose bags, lights; release actions | Power Apps | Power Apps canvas + Power Automate | Dataverse connector; Dataverse audit | Now | Andrew Tanui | AN-10 | 2026-11-05 | 2026-11-06 | 2 | Power Apps/Automate Premium | Not started
K01 | Control Centre | Model-driven app shell | Site map, master-data forms and views | Power Apps | Power Apps model-driven | Dataverse (native) | Now | Jones Alukwe | JO-02 | 2026-10-15 | 2026-10-19 | 3 | Power Apps/Automate Premium | Not started
K02 | Control Centre | Mapping BPF + F22 | Proposed → QC → Finance → Active; versions; coverage/conflict views | Power Apps | Model-driven BPF + Power Automate | Dataverse BPF; Approvals connector | Now | Jones Alukwe | JO-03 | 2026-10-21 | 2026-10-23 | 3 | Power Apps/Automate Premium | Not started
K03 | Control Centre | Contracts lineage + F26; provisional views | Allocations, relief, amendments; roll-over link; provisional stages | Power Apps | Model-driven + Power Automate | Dataverse | Now | Jones Alukwe | JO-04 | 2026-10-26 | 2026-10-27 | 2 | Power Apps/Automate Premium | Not started
K04 | Control Centre | Exception register | Views, SLA timer, comments, resolution codes | Power Apps | Power Apps model-driven | Dataverse SLA / timer control | Now | Jones Alukwe | JO-05 | 2026-10-27 | 2026-10-29 | 3 | Power Apps/Automate Premium | Not started
K05 | Control Centre | Reconciliation workspace | Custom page: L1/L2/L3 tabs, residual tiles, drill grid, side panel, actions | Power Apps | Custom page (canvas inside model-driven) | Dataverse connector | Now | Jones Alukwe | JO-06 | 2026-10-28 | 2026-11-03 | 5 | Power Apps/Automate Premium | Not started
K06 | Control Centre | Corrections + F27 weekly batch | Approval matrix, segregation of duties, Excel batch to system owners | Power Automate | Model-driven + Power Automate | Approvals connector; Excel Online; Outlook | Now (Excel batch) → Target: post via XBS/Comtras API | Jones Alukwe | JO-07 | 2026-11-02 | 2026-11-03 | 2 | Power Apps/Automate Premium | Not started
K07 | Control Centre | Downgrade worksheet + F25; SNI/shorts; feedback log | Monthly Low Grade candidates and approval | Power Apps | Custom page + Power Automate | Dataverse | Now | Jones Alukwe | JO-08 | 2026-11-03 | 2026-11-04 | 2 | Power Apps/Automate Premium | Not started
K08 | Control Centre | Sign-off BPF + F31 gate/lock + F32 pack | Six stages, automatic gate checks, period lock, pack distribution | Power Apps | Model-driven BPF + Power Automate | Dataverse real-time flow; Power BI export / Word template | Now | Jones Alukwe | JO-09 | 2026-11-04 | 2026-11-06 | 3 | Power Apps/Automate Premium | Not started
K09 | Control Centre | Embed Power BI | Dashboards inside the Control Centre | Power Apps | Model-driven + Power BI | Power BI embedded dashboard component | Now | Nicole Akinyi | NI-07 | 2026-11-04 | 2026-11-05 | 2 | Power BI Pro | Not started
M01 | Power BI | Semantic model | FactStock, FactRecon, FactException, FactMovement + dimensions | Data Analyst | Power BI Desktop (PBIP) | Dataverse connector (TDS endpoint); Import + DirectQuery | Now | Nicole Akinyi | NI-04 | 2026-10-26 | 2026-10-28 | 3 | Power BI Pro | Not started
M02 | Power BI | DAX measures | Residual, RI total, accuracy %, open/overdue exceptions | Data Analyst | Power BI Desktop | DAX | Now | Nicole Akinyi | NI-05 | 2026-10-28 | 2026-10-29 | 2 | Power BI Pro | Not started
M03 | Power BI | Eight report pages | Executive, stock, recon waterfall, exceptions, count performance, provisional/SNI, third parties, data quality | Data Analyst | Power BI Desktop / Service | Report authoring | Now | Nicole Akinyi | NI-06 | 2026-10-29 | 2026-11-04 | 5 | Power BI Pro | Not started
M04 | Power BI | RLS and workspace app | Department/warehouse security; app "NKG EA Stock Control" | Data Analyst | Power BI Service | Row-level security; deployment pipeline DEV→TEST→PROD | Now | Nicole Akinyi | NI-07 | 2026-11-04 | 2026-11-05 | 2 | Power BI Pro | Not started
M05 | Power BI | Scheduled refresh after intake | Refresh after F20 completes | Data Analyst | Power BI Service + Power Automate | Power BI connector "Refresh a dataset" (or Power BI REST API) | Now | Nicole Akinyi | NI-04 | 2026-10-28 | 2026-10-29 | 2 | Power BI Pro | Not started
M06 | Power BI | Month-end pack | Paginated report / Word template PDF | Data Analyst | Power BI paginated report (or Word template) | Power BI "Export to file" API via flow | Now | Nicole Akinyi | NI-08 | 2026-11-03 | 2026-11-06 | 4 | Power BI Pro | Not started
M07 | Power BI | Optional: Direct Lake model on Fabric | History and trends at scale on Lakehouse | Data Analyst | Microsoft Fabric + Power BI (optional) | Direct Lake on Link-to-Fabric tables | Target (phase 2, optional) | Nicole Akinyi | — | TBC | TBC |  | Fabric capacity (F-SKU) — confirm NKG has it | Not started
N01 | Copilot | Agent set-up and authentication | Stock Assistant in DEV; Entra auth; read-only | Copilot | Copilot Studio | Authenticate with Microsoft (acts as the user) | Now | Jones Alukwe | JO-10 | 2026-11-02 | 2026-11-03 | 2 | Copilot Studio | Not started
N02 | Copilot | Knowledge sources | Spec rules, BRD, SOPs, glossary in STK-Knowledge | Copilot | Copilot Studio + SharePoint | SharePoint knowledge source | Now | Jones Alukwe | JO-10 | 2026-11-02 | 2026-11-03 | 2 | Copilot Studio | Not started
N03 | Copilot | Actions (data lookups) | Outturn location, variance reasons, exceptions, contract, provisional | Copilot | Copilot Studio + Power Automate | Agent flows / Dataverse connector actions (user permissions) | Now | Jones Alukwe | JO-10 | 2026-11-03 | 2026-11-06 | 4 | Copilot Studio | Not started
N04 | Copilot | Topics T1–T5 | Where is outturn, why variance, count progress, my exceptions, explain a rule | Copilot | Copilot Studio | Topics + generative answers on knowledge only | Now | Jones Alukwe | JO-10 | 2026-11-03 | 2026-11-06 | 4 | Copilot Studio | Not started
N05 | Copilot | Topics T6–T10 | Contract, provisional, summarise comments, draft correction note, month-end readiness | Copilot | Copilot Studio | Topics | Now | Jones Alukwe | JO-11 | 2026-11-09 | 2026-11-11 | 3 | Copilot Studio | Not started
N06 | Copilot | Evaluation set (~30 questions) | Expected answers from parallel run; ≥ 90% pass, 100% on numbers | Copilot | Copilot Studio test pane | Manual + analytics review | Now | Nicole Akinyi | JO-11 | 2026-11-09 | 2026-11-11 | 3 | Copilot Studio | Not started
N07 | Copilot | Publish to Teams and Control Centre | Teams app; side pane in model-driven app; link from Stock Take Help | Copilot | Copilot Studio | Teams + Power Apps channel | Now | Jones Alukwe | JO-12 | 2026-11-12 | 2026-11-13 | 2 | Copilot Studio | Not started
O01 | Testing | Test data pack | Scenarios for every RI and EX code | Data Analyst | Excel + Dataverse | Loaded via the normal intake (email/SharePoint) | Now | Nicole Akinyi | NI-03 | 2026-10-19 | 2026-10-23 | 4 | Standard M365 | Not started
O02 | Testing | Tie-outs T1–T10 | Completeness, coverage, L1–L3, mass balance, report vs source, repeatability, parallel run, timeliness | Data Engineering | Dataverse + Power BI + Excel | Query comparisons; evidence in Git /test | Now | Denis Otieno | DO-17 | 2026-11-02 | 2026-11-06 | 5 | Standard M365 | Not started
O03 | Testing | SIT scripts and execution | Per area INT, MAP, CNT, EXC, COR, PRV, REG, 3P, CON, FB | Testing / QA | Excel / Azure DevOps Test Plans | Manual scripted testing | Now | Frankie Omasaja | FR-02, FR-03 | 2026-10-19 | 2026-11-06 | 14 | Standard M365 | Not started
O04 | Testing | Performance and security tests | 50k XBS lines, 20k count lines; SEC-01..05 | Testing / QA | Dataverse + Power Apps Monitor | Bulk load via dataflow; role-based test users | Now | Moses Masibo | MO-13 | 2026-11-03 | 2026-11-06 | 4 | Power Apps/Automate Premium | Not started
O05 | Testing | Power Apps Test Studio / Test Engine scripts | Automated regression for capture and close-location | Testing / QA | Power Apps Test Engine | YAML test plans | Now | Frankie Omasaja | FR-03 | 2026-10-28 | 2026-11-06 | 8 | Power Apps/Automate Premium | Not started
Formulas:
Work days = IFERROR(NETWORKDAYS([Start],[End],DATE(2026,10,20)),"")

## By Discipline
Summary by discipline and tool
Formulas over Development Tasks.
Discipline | Tasks | Work days | Main tools | Main people
Power Apps | 24 | 65 | Power Apps canvas (Stock Take app, Hub), model-driven (Control Centre), custom pages | William, Andrew, Jones
Power Automate | 13 | 42 | Cloud flows F01–F41, child flows, Approvals, Teams adaptive cards, Outlook | Denis, Jones, Andrew, William
UI | 5 | 11 | Power Apps component library, NKG theme, SVG icons, QR label template | William, Andrew, Jones
UX | 6 | 15 | Figma / prototypes, usability tests, accessibility checker | William, Jones, Frankie
Data Engineering | 26 | 101 | Dataverse, Power Query dataflows, custom connectors / gateway (target), Fabric (optional) | Denis, Moses
Data Analyst | 10 | 30 | Power BI (PBIP, DAX, RLS, paginated), Excel, Power Query | Nicole
Copilot | 7 | 20 | Copilot Studio, SharePoint knowledge, agent flows, Teams | Jones, Nicole
Architecture / ALM | 10 | 36 | Admin centre, solutions, pac CLI, pipelines, Git, Entra ID, DLP | Moses
Testing / QA | 3 | 26 | Test scripts, Power Apps Test Engine, Monitor | Frankie, Moses
Total | 104 | 346

## Integration Methods
How each source connects — now and later
We have no API access to XBS or Comtras yet, so we start with scheduled email files. Downstream logic does not change when APIs arrive.
Source | Now (interim) | Target | Owner | Ask / note
XBS (warehouse/outturn) | Scheduled report email (Excel/CSV) to shared mailbox → SharePoint → dataflow | REST API custom connector, or read-only SQL view via on-premises data gateway | XBS system owner / NKG IT | Ask: API documentation, read-only DB view, gateway server
Comtras / BRIC (526, 537, contracts) | Scheduled report email to shared mailbox | REST API or read-only SQL view via gateway | Comtras/BRIC owner / Finance | Ask: report scheduler access, API/DB access
Sun Systems (if needed for values) | Monthly export email | Sun connector / SQL view via gateway | Finance | Scope to confirm
SNI, provisional, third-party balances | Excel templates emailed by Logistics/Trade | Remain email/form-based (no system of record) | Logistics, Trade | Templates in STK-Intake/Templates
Physical count | Stock Take app writes directly to Dataverse | Same | Operations | —
Corrections back to XBS/Comtras | Weekly Excel batch emailed to system owners; confirmed by next snapshot | Post via API when write access is granted | System owners | Never write to source systems without approval
Power BI | Dataverse connector (TDS endpoint), scheduled refresh triggered by flow | Direct Lake on Fabric (optional) | Pathways / NKG IT | —