## Read Me
Stocktake Optimization — Team Work Plan
NKG East Africa / Ibero Kenya · Pathways Technologies · prepared 9 Oct 2026 · plan V1.0
How to use this workbook
Master Plan | Every task with owner, support, dates, dependencies, deliverable and "done when". Update Status (drop-down) and % Done here only.
Team Summary | Counts, workload and next due date per person — all formulas from Master Plan.
Person sheets | One sheet per team member (live links to Master Plan rows) — send each person their tab.
Next Week (12–16 Oct) | Day-by-day plan for every person for the first build week.
Gantt | Weekly timeline; bars shade automatically from Start/End dates; green = complete.
Milestones | Key dates the sponsor tracks.
NKG Actions | What we need from NKG, by when, and which of our tasks it blocks.
Meetings & Rhythm | Recurring ceremonies (stand-up, status, reviews, steering).
Holidays | Public holidays excluded from "Work days" (Mashujaa Day Tue 20 Oct falls in Sprint 1).
Red text | Item still to be confirmed with NKG or the team.
Team and responsibilities
Name | Role | Owns
Daphne Okwaro | Project Manager / Data Analytics Lead | Plan, NKG decisions, access, stakeholder management, status reporting, SIT/UAT/training/cutover coordination
Moses Masibo | Solution Architect | Environments, solutions, ALM and Git, security model, data-model and engine design review, code review, PROD readiness
Denis Otieno | Data Engineer | Email intake, validation, dataflows, Dataverse tables, master-data migration, reconciliation engine L1–L3, rules, tie-outs
Nicole Akinyi | Data Analyst | Data profiling, mapping coverage, test data, Power BI model and reports, month-end pack, parallel-run analysis
William Imo | Power Apps Developer | Stock Take app (counter phone/tablet app), offline sync, count flows F11–F12, counter training
Andrew Tanui | Power Apps Developer | Stock Management Hub (plan, run, review, close, third parties, registers, admin), Hub flows
Jones Alukwe | Power Apps Developer / Copilot Developer | Stock Control Centre (model-driven), BPFs, exceptions, corrections, sign-off gate, Copilot Stock Assistant
Frankie Omasaja | QA / Test & Documentation — role to confirm | SIT scripts and execution, defect log, UAT scripts, user guides and training material formatting
Phases
Phase | Dates | Exit criteria
0 Discovery | 1 – 9 Oct | Sessions held, BRD V1.1, spec, mockups (done)
1 Design | 5 – 16 Oct | BRD/design signed; decisions OD1–OD5, OD9 closed; environments and Git ready
2 Sprint 1 | 12 – 23 Oct | Intake, tables, master data, app capture, wizard, mapping BPF demoed
3 Sprint 2 | 26 Oct – 6 Nov | Engine L1–L3, exceptions, corrections, workspace, sign-off, Power BI, Copilot T1–T5
4 SIT + parallel run | 26 Oct – 6 Nov | Tie-outs T1–T10 = 0; October count run in new solution (2–4 Nov)
5 Training | 9 – 13 Nov | ≥ 90% of named users trained; UAT release deployed
6 UAT | 16 – 27 Nov | UAT signed by every department
7 Cutover | 23 Nov – 3 Dec | PROD live; feeds clean 3 days; baseline approved; first live count 1–3 Dec
8 Hypercare | 1 – 11 Dec | First sign-off with residual = 0 by WD7 (9 Dec); handover complete
9 Acceptance | 14 – 17 Dec | Formal acceptance 17 Dec
Capacity watch | Jones (Control Centre + Copilot) and Andrew (Hub + parallel-run support) are heaviest in 2–6 Nov. Copilot topics T6–T10 are deliberately in training week; if Jones slips, Copilot moves into the UAT window (no reconciliation feature depends on it). Frankie's role is assumed as QA / documentation — confirm.

## Team Summary
Team Summary
All figures are formulas over Master Plan.
Name | Role | Tasks owned | Complete | In progress | Not started | Blocked / at risk | Overdue | Owned work days | % complete (avg) | Next open task due | Also supporting (tasks)
Daphne Okwaro | Project Manager / Data Analytics Lead | 27 | 6 | 1 | 20 | 0 | 0 | 82 | 23.15% | 2026-10-09 | 13
Moses Masibo | Solution Architect | 18 | 0 | 0 | 18 | 0 | 0 | 66 | 0% | 2026-10-13 | 24
Denis Otieno | Data Engineer | 23 | 0 | 0 | 23 | 0 | 0 | 81 | 0% | 2026-10-13 | 21
Nicole Akinyi | Data Analyst | 12 | 0 | 0 | 12 | 0 | 0 | 46 | 0% | 2026-10-16 | 26
William Imo | Power Apps Developer | 13 | 0 | 0 | 13 | 0 | 0 | 41 | 0% | 2026-10-13 | 12
Andrew Tanui | Power Apps Developer | 13 | 0 | 0 | 13 | 0 | 0 | 37 | 0% | 2026-10-13 | 14
Jones Alukwe | Power Apps Developer / Copilot Developer | 14 | 0 | 0 | 14 | 0 | 0 | 47 | 0% | 2026-10-13 | 14
Frankie Omasaja | QA / Test & Documentation — role to confirm | 6 | 0 | 0 | 6 | 0 | 0 | 35 | 0% | 2026-10-16 | 12
Total |  | 126 | 6 | 1 | 119 | 0 | 0 | 435
Formulas:
Next open task due = IFERROR(1/(1/MINIFS('Master Plan'!$I5:I130,'Master Plan'!$F5:F130,[Name],'Master Plan'!$O5:O130,"<>Complete")),"—")

## Master Plan
Stocktake Optimization — Master Task Plan (NKG East Africa)
Edit Status and % Done here only — person sheets, Gantt and Team Summary update from this sheet. Red text = to confirm with NKG.
ID | Phase | Workstream | Task | Detailed description / steps | Owner | Support | Start | End | Work days | Depends on | Deliverable / output | Done when (acceptance) | Spec ref | Status | % Done | Overdue? | Notes / blockers
PM-01 | 0 Discovery | Project management | Project kick-off and warehouse walk-through | Kick-off with NKG; walk the warehouse floor; observe stacking, rows A–G / sections 1–14, bag tags, pockets, lights. | Daphne Okwaro | All | 2026-10-01 | 2026-10-01 | 1 |  | Kick-off notes | Held with NKG stakeholders | — | Complete | 100%
PM-02 | 0 Discovery | Project management | Discovery sessions: Finance, Warehouse & Operations, Trade & QC, Logistics | Run four sessions; record and transcribe; capture process, pain points, reports, data owners. | Daphne Okwaro | Moses Masibo, Denis Otieno, Nicole Akinyi | 2026-10-02 | 2026-10-08 | 5 | PM-01 | Recordings + notes | All four sessions held and transcribed | BRD | Complete | 100%
PM-03 | 0 Discovery | Project management | BRD V1.1 (red = items to confirm) | Update the BRD from all recordings; mark unconfirmed items in red. | Daphne Okwaro | Nicole Akinyi | 2026-10-05 | 2026-10-09 | 5 | PM-02 | STOCKTAKE_BRD_V1.1.docx | Issued to team | BRD | Complete | 100%
PM-04 | 0 Discovery | Design | Developer Build Specification V1.0 + screen mockups | Write the build specification (Sections 1–22 + appendices) and 10 screen mockups. | Daphne Okwaro | Moses Masibo | 2026-10-07 | 2026-10-09 | 3 | PM-03 | Spec V1.0 + mockups PDF | Issued to team | All | Complete | 100%
PM-05 | 0 Discovery | Access | System access request sent (NKG emails, Power Platform, Git, ITB environment) | Request NKG accounts for all 8 team members, environment maker access, Git, legacy ITB environment. | Daphne Okwaro | Moses Masibo | 2026-10-05 | 2026-10-06 | 2 |  | Access request email | Sent; ITB environment access received | 16 | Complete | 100%
PM-06 | 0 Discovery | Weekly status | Weekly status report #1 | Status email (Word + HTML) to NKG. | Daphne Okwaro |  | 2026-10-02 | 2026-10-02 | 1 |  | Status report | Sent | — | Complete | 100%
PM-10 | 1 Design | Weekly status | Weekly status report #2 | Progress: discovery complete, BRD V1.1, build spec, mockups; next week: design sign-off, decisions OD1–OD9, sprint 1 start. | Daphne Okwaro |  | 2026-10-09 | 2026-10-09 | 1 | PM-04 | Status report | Sent to NKG distribution list | — | In progress | 25%
PM-11 | 1 Design | Stakeholders | Circulate BRD V1.1, Build Spec and mockups to NKG for review | Email to Carol, Maina, Mathew, Denis Koech, department leads; ask for written comments by Wed 14 Oct; attach mockups PDF. | Daphne Okwaro |  | 2026-10-12 | 2026-10-12 | 1 | PM-04 | Review email | Sent; every reviewer acknowledged | — | Not started | 0%
PM-12 | 1 Design | Decisions | Open-decision log OD1–OD9 (red items) | Create decision log (decision, options, recommendation, owner, needed-by). Book 30-min calls per owner. Chase daily until closed. OD1 cut-off rule; OD2 unit rule (pocket, lights); OD3 Low Grade posting; OD4 provisional stock location; OD5 count tolerance; OD6 write-off thresholds; OD7 sign-off order; OD8 Copilot approval; OD9 licensing/environments. | Daphne Okwaro | Moses Masibo | 2026-10-12 | 2026-10-16 | 5 | PM-11 | Decision log | OD1–OD5 and OD9 closed by 16 Oct; OD6–OD8 by 23 Oct | 22.3 | Not started | 0%
PM-13 | 1 Design | Stakeholders | Design walkthrough with NKG (mockups + zero-variance model) | 2-hour session, Digitization Project Team Boardroom / Teams. Demo mockups screen by screen; explain residual = 0 gate; collect feedback. | Daphne Okwaro | Moses Masibo, William Imo, Andrew Tanui, Jones Alukwe | 2026-10-13 | 2026-10-13 | 1 | PM-11 | Feedback list | Feedback logged and triaged into backlog | 3, 4, 9–14 | Not started | 0%
PM-14 | 1 Design | Stakeholders | Obtain BRD and design sign-off | Update BRD/spec for walkthrough feedback (V1.2); obtain written sign-off from the approval table. | Daphne Okwaro | Moses Masibo | 2026-10-14 | 2026-10-16 | 3 | PM-13, PM-12 | Signed BRD V1.2 + Spec V1.1 | Signatures/approval emails received | Doc control | Not started | 0%
PM-15 | 1 Design | Data feeds | Formal data-feed request to XBS and Comtras/BRIC owners | Request: (1) sample files for every feed S1–S15 by 14 Oct; (2) scheduled daily email to shared mailbox at 07:00 with subject STK¦<SOURCE>¦<YYYYMMDD>¦<HHMM>; (3) named backup sender. | Daphne Okwaro | Denis Otieno | 2026-10-12 | 2026-10-14 | 3 |  | Feed request email + owner list | Every feed has a named owner and a start date | 7.1–7.2 | Not started | 0%
PM-16 | 1 Design | Access | Licensing and environment confirmation with NKG IT | Confirm Power Apps Premium for Hub/Control Centre users, service account stk.svc, shared mailbox, DEV/UAT/PROD Dataverse environments, Copilot Studio availability. | Daphne Okwaro | Moses Masibo | 2026-10-12 | 2026-10-16 | 5 |  | Confirmation email from NKG IT | Licences and environments confirmed in writing | 15, 16 | Not started | 0%
MO-01 | 1 Design | Architecture | Inventory the ITB (John Nyongesa) solution | Export managed solution "NKG Stock Solution" and all flows; list every app, flow, dataflow, table, SharePoint list, connection and owner; note what to keep/rebuild/retire. | Moses Masibo | Denis Otieno | 2026-10-12 | 2026-10-13 | 2 | PM-05 | ITB inventory sheet + exported zip in Git /legacy | Inventory reviewed with team | 2, 16.4 | Not started | 0%
MO-02 | 1 Design | Architecture | Ownership-transfer plan for ITB apps and flows | Plan transfer of flows/apps from the external account to stk.svc so nothing stops when the external account is removed; agree date with NKG IT. | Moses Masibo |  | 2026-10-13 | 2026-10-14 | 2 | MO-01 | Transfer plan | NKG IT agreed date | 16.4 | Not started | 0%
MO-03 | 1 Design | Environments | Request/confirm DEV, UAT, PROD environments and DLP policy | Dataverse in each; DLP Business group: Dataverse, SharePoint, Outlook, Teams, Approvals, Power BI; block consumer connectors. | Moses Masibo | Daphne Okwaro | 2026-10-12 | 2026-10-16 | 5 | PM-16 | Environments live | Team can open DEV as makers | 16.1, 15.2 | Not started | 0%
MO-04 | 1 Design | ALM | Create publisher (prefix stk) and solutions in DEV | STK Core, STK Apps, STK Automation, STK Copilot; environment-variable and connection-reference standards. | Moses Masibo |  | 2026-10-14 | 2026-10-15 | 2 | MO-03 | Solutions in DEV | All devs building inside solutions | 16.2, App. D | Not started | 0%
MO-05 | 1 Design | ALM | Git repository and branching | Create repo (/solutions, /powerbi, /docs, /test, /legacy); main/develop/feature branches; PR rule (Moses reviews); access for all 8. | Moses Masibo |  | 2026-10-13 | 2026-10-15 | 3 | PM-05 | Git repo | First commit by every developer | 16.3 | Not started | 0%
MO-06 | 1 Design | Data model | Data-model review (34 tables, keys, alternate keys) | Review with Denis: columns, choice sets, relationships, alternate keys (stk_localid, rule+key), audit settings. | Moses Masibo | Denis Otieno | 2026-10-14 | 2026-10-16 | 3 | MO-04 | Approved ERD | Signed off by Moses | 6 | Not started | 0%
NI-01 | 1 Design | Data analysis | Profile sample files from every feed | For each file: row counts, keys, duplicates, blanks, grade/quality codes, units, date formats; compare to Appendix E templates. | Nicole Akinyi | Denis Otieno | 2026-10-13 | 2026-10-16 | 4 | PM-15 | Profiling report | Issues list sent to data owners | 7.2, App. E | Not started | 0%
DO-01 | 1 Design | Data engineering | Review ITB dataflows and staging | Understand current dataflows → Dataverse staging → SharePoint lists; note reusable logic and known failures. | Denis Otieno | Moses Masibo | 2026-10-12 | 2026-10-13 | 2 | PM-05 | Notes in Git /docs | Reviewed with Moses | 2 | Not started | 0%
DO-02 | 1 Design | Data engineering | Finalise intake file templates and column mappings | Agree exact column names per feed with owners; publish templates in STK-Intake/Templates. | Denis Otieno | Nicole Akinyi | 2026-10-14 | 2026-10-16 | 3 | NI-01 | Templates S1–S15 | Owners confirm they can produce them | App. E | Not started | 0%
WI-01 | 1 Design | Stock Take app | Review ITB Stock Take app | Walk every screen and formula; note delegation warnings, performance, what to keep/rebuild. | William Imo |  | 2026-10-12 | 2026-10-13 | 2 | PM-05 | Review notes | Shared at stand-up | 9 | Not started | 0%
AN-01 | 1 Design | Hub | Review ITB Stock Management app | Admin, Import, Dashboard, Reports, Stock Takes approvals: document logic and data sources. | Andrew Tanui |  | 2026-10-12 | 2026-10-13 | 2 | PM-05 | Review notes | Shared at stand-up | 10 | Not started | 0%
JO-01 | 1 Design | Control Centre / Copilot | Copilot Studio and model-driven readiness check | Check Copilot Studio availability/licensing in tenant; list knowledge sources; draft model-driven site map. | Jones Alukwe | Moses Masibo | 2026-10-12 | 2026-10-13 | 2 | PM-16 | Readiness note | Input to OD8 | 11, 14 | Not started | 0%
WI-02 | 1 Design | Shared UI | Shared component library (NKG theme) | Header, buttons, chips, tiles, input fields in NKG Green #006330 palette; published as component library for all canvas apps. | William Imo | Andrew Tanui | 2026-10-13 | 2026-10-14 | 2 | MO-04 | Component library | Used by Stock Take app and Hub | 9.1 | Not started | 0%
FR-01 | 1 Design | Testing | Test strategy and defect process | Defect log (severity 1–4, owner, status), test case template, SIT script structure per area. | Frankie Omasaja | Daphne Okwaro | 2026-10-13 | 2026-10-16 | 4 | PM-04 | Test strategy + defect log | Approved by PM | 18 | Not started | 0%
PM-20 | 2 Sprint 1 | Delivery | Sprint 1 planning | Assign Sprint 1 stories; confirm capacity (Mashujaa Day Tue 20 Oct is a public holiday). | Daphne Okwaro | All | 2026-10-12 | 2026-10-12 | 1 |  | Sprint 1 board | Every story has owner and estimate | 19 | Not started | 0%
MO-07 | 2 Sprint 1 | Environments | Shared mailbox and SharePoint STK-Intake site | With NKG IT: create mailbox stocktake.data@nkg.coffee; library STK-Intake with Incoming/Rejected/Processed/Templates; permissions for stk.svc. | Moses Masibo | Denis Otieno | 2026-10-15 | 2026-10-16 | 2 | PM-16 | Mailbox + library | Test email lands and is readable by flow | 7.1 | Not started | 0%
DO-03 | 2 Sprint 1 | Data model | Create Dataverse tables in STK Core | Build 34 stk_ tables with columns, choices, alternate keys, relationships, auditing; stk_config seeded with keys. | Denis Otieno | Moses Masibo | 2026-10-15 | 2026-10-21 | 4 | MO-06 | Tables in DEV | ERD = DEV schema; solution exported to Git | 6 | Not started | 0%
DO-04 | 2 Sprint 1 | Intake | F01 Receive intake email | Trigger on shared mailbox; parse subject; sender allow-list; save attachment as <SOURCE>_<YYYYMMDD>_<HHMM>.<ext>; log to stk_loadlog. | Denis Otieno |  | 2026-10-19 | 2026-10-21 | 2 | MO-07, DO-03 | Flow F01 | 10 test emails processed correctly, bad sender rejected | 12.2 | Not started | 0%
DO-05 | 2 Sprint 1 | Intake | F02 Validate file (V1–V7) | Columns, types, dates, row counts, duplicates, control totals, period; move to Rejected + reply with reason, or Processed + trigger load. | Denis Otieno | Nicole Akinyi | 2026-10-21 | 2026-10-23 | 3 | DO-04 | Flow F02 | Each V-rule has a failing test file that is rejected with the right reason | 7.3 | Not started | 0%
DO-06 | 2 Sprint 1 | Intake | Dataflows to staging + F03 load | One dataflow per source (XBS stock, XBS movements, 526, 537, contracts, SNI, provisional, third-party); F03 refresh, poll, snapshot header, row-count check. | Denis Otieno |  | 2026-10-19 | 2026-10-23 | 4 | DO-03 | Dataflows + F03 | T1 completeness passes for every sample file | 7, 12.2 | Not started | 0%
DO-07 | 2 Sprint 1 | Master data | Master-data migration | Load warehouses, locations, zones, grades, quality codes, packing types, secondary/primary baskets, contracts, mappings from ITB lists and Comtras. | Denis Otieno | Nicole Akinyi | 2026-10-21 | 2026-10-23 | 3 | DO-03 | Master data in DEV | Counts tie to sources; T2 coverage report produced | 7.5 | Not started | 0%
NI-02 | 2 Sprint 1 | Data analysis | Mapping coverage analysis | Outturn → grade → secondary → primary basket; list unmapped and conflicting outturns for Trade/QC with eq60 impact. | Nicole Akinyi | Denis Otieno | 2026-10-15 | 2026-10-21 | 4 | NI-01 | Coverage report + unmapped list | List sent to Trade and QC | 8.2, 11.2 | Not started | 0%
NI-03 | 2 Sprint 1 | Testing | Build test data sets | Scenarios for every RI code and EX01–EX20: found-elsewhere, pockets, lights, timing, third-party, SNI, provisional, wrong basket, roll-over. | Nicole Akinyi | Frankie Omasaja | 2026-10-19 | 2026-10-23 | 4 | DO-02 | Test data pack in Git /test | Each scenario has expected result | 8.4, 8.5, 18 | Not started | 0%
WI-03 | 2 Sprint 1 | Stock Take app | S1 Sign-in/version check and S2 Home | SSO, role & warehouse load, App.MinVersion check; Home tiles, banner with cut-off and time left. | William Imo |  | 2026-10-15 | 2026-10-16 | 2 | WI-02 | Screens S1–S2 | Demoed at stand-up | 9.2 | Not started | 0%
WI-04 | 2 Sprint 1 | Stock Take app | S3 My Assignments and S4 Location (QR) | Assignments grouped by zone with status chips; QR scan or pick; Start count / Mark empty / Cannot access (reason). | William Imo |  | 2026-10-19 | 2026-10-22 | 3 | WI-03, DO-03 | Screens S3–S4 | QR test labels scan on 2 devices | 9.2 | Not started | 0%
WI-05 | 2 Sprint 1 | Stock Take app | S5 Capture screen | Outturn scan/search (StartsWith, delegable); Expected / Found elsewhere / Not in list / Unidentified (photo); grade from mapping; packing default; bags + pocket; live Units/Kg/Eq60; category. | William Imo | Denis Otieno | 2026-10-21 | 2026-10-23 | 3 | WI-04 | Screen S5 | AC-9.2: 20 test lines equal engine calculation | 9.3 | Not started | 0%
AN-02 | 2 Sprint 1 | Hub | Admin screens | Warehouses, grades, packing types, unit rules (with approval), stk_config editor with change reason, users and roles. | Andrew Tanui |  | 2026-10-15 | 2026-10-19 | 3 | WI-02, DO-03 | Admin area | Config change writes audit record | 10.8 | Not started | 0%
AN-03 | 2 Sprint 1 | Hub | Location generator + QR labels | Generate A01–G14 per warehouse; deactivate not delete; print QR label sheet (PDF via Word template flow). | Andrew Tanui | William Imo | 2026-10-21 | 2026-10-22 | 2 | AN-02 | Generator + label PDF | 98 labels generated for Main Warehouse test | 10.8 | Not started | 0%
AN-04 | 2 Sprint 1 | Hub | Stock take wizard (5 steps) + F10 notify | Type, cut-off, locked snapshot, scope, counters, review & create; pre-checks (feeds, lock, EX20, mapping); creates stocktake, assignments, hidden expected lines; F10 Teams/email. | Andrew Tanui | Denis Otieno | 2026-10-21 | 2026-10-26 | 4 | AN-03, DO-06 | Wizard + F10 | Stock take created from test snapshot; counters notified | 10.2 | Not started | 0%
JO-02 | 2 Sprint 1 | Control Centre | Model-driven app shell | Site map (Master data, Stock positions, Reconciliation, Exceptions, Close, Insights); main forms and views for master-data tables. | Jones Alukwe |  | 2026-10-15 | 2026-10-19 | 3 | DO-03 | App shell | All tables navigable | 11.1 | Not started | 0%
JO-03 | 2 Sprint 1 | Control Centre | Mapping BPF + F22 + versioning | Proposed → QC verified → Finance approved → Active; effective dates; coverage and conflict views; F22 notifications; overlap blocked. | Jones Alukwe | Nicole Akinyi | 2026-10-21 | 2026-10-23 | 3 | JO-02 | Mapping BPF | UAT-03 path works end to end in DEV | 11.2 | Not started | 0%
MO-08 | 2 Sprint 1 | Security | Security model build | Entra groups SG-STK-<Role>; 10 Dataverse roles; team mapping; field security (expected qty hidden from Counter, approvals, config). | Moses Masibo |  | 2026-10-19 | 2026-10-23 | 4 | DO-03 | Roles + groups | Role test: counter cannot read expected qty | 15 | Not started | 0%
MO-09 | 2 Sprint 1 | ALM | Build and deploy pipeline DEV → UAT | pac CLI export/unpack/commit; managed build; deployment settings per environment. | Moses Masibo |  | 2026-10-21 | 2026-10-23 | 3 | MO-05 | Pipeline | First managed deploy to UAT succeeds | 16.3 | Not started | 0%
FR-02 | 2 Sprint 1 | Testing | Write SIT scripts | Scripts for INT, MAP, CNT, EXC, COR, PRV, REG, 3P, CON, FB areas with steps, test data and expected results. | Frankie Omasaja | Nicole Akinyi | 2026-10-19 | 2026-10-23 | 4 | FR-01, NI-03 | SIT script pack | Reviewed by Moses | 18.1, App. B | Not started | 0%
PM-21 | 2 Sprint 1 | Delivery | Sprint 1 review / demo to NKG | Demo intake, master data, Stock Take app capture, wizard, mapping BPF. | Daphne Okwaro | All | 2026-10-23 | 2026-10-23 | 1 |  | Demo + feedback | NKG feedback logged | 19 | Not started | 0%
PM-30 | 3 Sprint 2 | Delivery | Sprint 2 planning | Carry-over from Sprint 1; confirm parallel-run plan. | Daphne Okwaro | All | 2026-10-26 | 2026-10-26 | 1 | PM-21 | Sprint 2 board | Stories assigned | 19 | Not started | 0%
DO-08 | 3 Sprint 2 | Intake | F04 missing-feed, F05 reprocess, F06 lock snapshot | F04 08:00 check → EX20; F05 Hub button; F06 locks month-end snapshot. | Denis Otieno |  | 2026-10-26 | 2026-10-27 | 2 | DO-06 | Flows F04–F06 | Missing test feed raises EX20 | 12.2 | Not started | 0%
DO-09 | 3 Sprint 2 | Engine | Normalisation and mass balance | Convert all positions to kg/eq60 with unit rules; opening + receipts − issues ± adjustments = closing per outturn. | Denis Otieno | Moses Masibo | 2026-10-26 | 2026-10-28 | 3 | DO-07 | Engine step 1 | T6 passes on test data | 4.2–4.3 | Not started | 0%
DO-10 | 3 Sprint 2 | Engine | L1 Physical vs XBS (F30) | Compare count vs locked snapshot; attach RIs in order TIMING, LOCATION, CORRECTION-PENDING, UNIT-RULE, PACKING, PROVISIONAL, THIRD-PARTY, REMNANT; raise EX01/EX02. | Denis Otieno |  | 2026-10-27 | 2026-10-29 | 3 | DO-09 | L1 engine | Worked example KCS7948 gives residual 0 | 4.4, 8.3 | Not started | 0%
DO-11 | 3 Sprint 2 | Engine | L2 XBS vs Comtras | SNI add-back, provisional, registers; RIs DOWNGRADE, PURCHASE-PENDING, WRONG-BASKET, ROLLOVER, BRIC-PENDING, SHORT-DELIVERY; EX15. | Denis Otieno | Nicole Akinyi | 2026-10-29 | 2026-11-03 | 4 | DO-10 | L2 engine | T4 passes on test data | 4.5 | Not started | 0%
DO-12 | 3 Sprint 2 | Engine | L3 Baskets vs Contracts | Basket balances vs contract open quantities incl. roll-over lineage. | Denis Otieno |  | 2026-11-02 | 2026-11-04 | 3 | DO-11 | L3 engine | T5 passes | 4.6 | Not started | 0%
DO-13 | 3 Sprint 2 | Rules | F20 daily rules EX05–EX20 + upsert child flow | Rule child flows return (rule, key, qty, details); upsert on alternate key; auto-close when cleared. | Denis Otieno | Jones Alukwe | 2026-10-28 | 2026-11-04 | 6 | DO-08 | F20 + rules | Each EX code fires and auto-closes on test data | 8.5, 12.3 | Not started | 0%
DO-14 | 3 Sprint 2 | Automation | F23 provisional auto-match, F28 correction posting check | Close provisional on matching XBS receipt; mark corrections Posted from next snapshot or raise EX13. | Denis Otieno |  | 2026-11-03 | 2026-11-05 | 3 | DO-11 | Flows F23, F28 | Test receipt closes provisional; unposted correction ages to EX13 | 12.2 | Not started | 0%
NI-04 | 3 Sprint 2 | Power BI | Power BI model | Dataverse connection; FactStock, FactRecon, FactException, FactMovement; dims; Import + DirectQuery split. | Nicole Akinyi |  | 2026-10-26 | 2026-10-28 | 3 | DO-03 | PBIP in Git | Model refreshes in DEV workspace | 13.1 | Not started | 0%
NI-05 | 3 Sprint 2 | Power BI | DAX measures | Eq60 by source, Raw Diff, RI Total, Corrections, Residual, Residual OK, Count Accuracy %, Open/Overdue exceptions. | Nicole Akinyi |  | 2026-10-28 | 2026-10-29 | 2 | NI-04 | Measures | Measures match hand-calculated test values | 13.2 | Not started | 0%
NI-06 | 3 Sprint 2 | Power BI | Eight report pages | Executive, Stock position, Reconciliation waterfall, Exceptions, Count performance, Provisional & SNI, Third parties, Data quality. | Nicole Akinyi |  | 2026-10-29 | 2026-11-04 | 5 | NI-05 | Report | Matches mockup 08; reviewed by PM | 13.3 | Not started | 0%
NI-07 | 3 Sprint 2 | Power BI | RLS, workspace app, embed | RLS by department/warehouse; publish workspace app "NKG EA Stock Control"; embed in Control Centre with Jones. | Nicole Akinyi | Jones Alukwe | 2026-11-04 | 2026-11-05 | 2 | NI-06 | Workspace app | Role test: Logistics sees only Logistics pages | 13.3 | Not started | 0%
NI-08 | 3 Sprint 2 | Reporting | Month-end pack template (F32) | Paginated report / Word template: residuals, waterfall, exceptions, corrections, sign-off history. | Nicole Akinyi | Jones Alukwe | 2026-11-03 | 2026-11-06 | 4 | NI-06 | Pack template | PDF generated from test period | 12.2 | Not started | 0%
WI-06 | 3 Sprint 2 | Stock Take app | S6 Location summary and close; F11 bulk submit | Review lines, totals, edit before submit, close location; F11 for >50 lines. | William Imo |  | 2026-10-26 | 2026-10-27 | 2 | WI-05 | S6 + F11 | Close writes lines and status in one action | 9.4 | Not started | 0%
WI-07 | 3 Sprint 2 | Stock Take app | Offline queue and sync (S9) | LoadData/SaveData queue; 30-s timer sync; Failed state with reason; idempotent on stk_localid. | William Imo | Moses Masibo | 2026-10-27 | 2026-10-29 | 3 | WI-06 | Offline sync | AC-9.3: 100 offline lines sync with 0 duplicates, 0 loss | 9.5 | Not started | 0%
WI-08 | 3 Sprint 2 | Stock Take app | Smart warnings + F12 not-in-list alert | Duplicate in location, counted elsewhere, implausible qty, pocket ≥ bag, closed location; F12 supervisor alert with photo. | William Imo |  | 2026-10-28 | 2026-10-30 | 3 | WI-05 | Warnings + F12 | Each warning shown with test data | 9.3.3 | Not started | 0%
WI-09 | 3 Sprint 2 | Stock Take app | S7 Recount (double-blind), S8 100% issue/receive, S10 Help | Recount task view; issue/receive during count; Help with rules card and Stock Assistant link. | William Imo |  | 2026-10-29 | 2026-11-02 | 3 | WI-08 | Screens S7, S8, S10 | Recount goes to a different counter | 9.2 | Not started | 0%
WI-10 | 3 Sprint 2 | Stock Take app | Device and floor testing | Test on NKG phones/tablets — models to confirm in far zones and Wi-Fi dead spots; glove test; font sizes. | William Imo | Frankie Omasaja | 2026-11-03 | 2026-11-05 | 3 | WI-07 | Device test report | No blocker on any device | 9.1 | Not started | 0%
AN-05 | 3 Sprint 2 | Hub | Assignments board and auto-balance | Assign by zone; auto-balance by expected line count; block self-recount. | Andrew Tanui |  | 2026-10-26 | 2026-10-27 | 2 | AN-04 | Assignments board | Balanced split for 98 locations | 10.2 | Not started | 0%
AN-06 | 3 Sprint 2 | Hub | Live monitor | KPIs, floor map, progress by counter, in-XBS-not-counted, counted-not-in-XBS; 60-s refresh. | Andrew Tanui |  | 2026-10-27 | 2026-10-29 | 3 | AN-05, WI-06 | Live monitor | AC-9.4: new line visible within 60 s | 10.3 | Not started | 0%
AN-07 | 3 Sprint 2 | Hub | F13 location variance check, recount and unidentified queues | Compare with hidden expected; out of tolerance → recount to different counter; supervisor queues. | Andrew Tanui | Denis Otieno | 2026-10-29 | 2026-10-30 | 2 | AN-06 | F13 + queues | Out-of-tolerance location creates recount | 10.4, 12.2 | Not started | 0%
AN-08 | 3 Sprint 2 | Hub | Variance review, manual approvals, close count + F14 | Supervisor actions with comment; close only when all closed/recounts done; F14 freezes lines and triggers L1. | Andrew Tanui | Denis Otieno | 2026-11-02 | 2026-11-03 | 2 | AN-07, DO-10 | Review + close | AC-9.5: close to L1 with no manual step | 10.4–10.5 | Not started | 0%
AN-09 | 3 Sprint 2 | Hub | Third-party confirmations + F15 | Balance statements M−5, capture replies, chase M−3, escalate M−2, EX10/EX11. | Andrew Tanui |  | 2026-11-04 | 2026-11-05 | 2 | DO-13 | Screen + F15 | Test third party with difference creates RI-THIRD-PARTY | 10.6 | Not started | 0%
AN-10 | 3 Sprint 2 | Hub | Registers + F24, Imports & load log, Audit | Disputed, franchise, ex-office, sweepings, loose bags, lights; release actions; upload-to-Incoming fallback; audit view. | Andrew Tanui |  | 2026-11-05 | 2026-11-06 | 2 | AN-09 | Screens + F24 | Release creates correction where required | 10.7, 10.9 | Not started | 0%
JO-04 | 3 Sprint 2 | Control Centre | Contracts lineage + F26, provisional pipeline views | Contract form with allocations, relief, amendments; roll-over lineage; provisional stages and ageing. | Jones Alukwe |  | 2026-10-26 | 2026-10-27 | 2 | JO-02 | Forms + F26 | Roll-over test links successor contract | 11.4–11.5 | Not started | 0%
JO-05 | 3 Sprint 2 | Control Centre | Exception register + F21 notifications | Views (my, team, overdue, closed); SLA timer; comments table; resolution codes; F21 owner alerts, 16:00 reminders, escalation. | Jones Alukwe |  | 2026-10-27 | 2026-10-29 | 3 | DO-13 | Register + F21 | Overdue test exception escalates to manager | 11.8 | Not started | 0%
JO-06 | 3 Sprint 2 | Control Centre | Reconciliation workspace (custom page) | Tabs L1/L2/L3; tiles raw/RIs/corrections/residual; drill grid; side panel (RIs, exceptions, comments); Attach RI, Propose correction, Re-run. | Jones Alukwe | Denis Otieno | 2026-10-28 | 2026-11-03 | 5 | DO-10 | Workspace | Matches mockup 04 with live DEV data | 11.6 | Not started | 0%
JO-07 | 3 Sprint 2 | Control Centre | Corrections + approval matrix + F27 batch | Correction form, SoD (proposer ≠ approver), approval by type/value, weekly Excel batch per system owner. | Jones Alukwe |  | 2026-11-02 | 2026-11-03 | 2 | JO-05 | Corrections + F27 | Same-user approval is blocked | 11.9, 15.2 | Not started | 0%
JO-08 | 3 Sprint 2 | Control Centre | Downgrade worksheet + F25; SNI/shorts views; feedback log | Monthly Low Grade candidates; approval creates mapping versions + basket-transfer correction. | Jones Alukwe | Nicole Akinyi | 2026-11-03 | 2026-11-04 | 2 | JO-03 | Worksheet + views | Approved downgrade shows RI-DOWNGRADE in L2 | 11.3, 11.7, 11.10 | Not started | 0%
JO-09 | 3 Sprint 2 | Control Centre | Sign-off BPF + F31 gate/lock + F32 trigger | Six stages with automatic gate checks; final locks period and publishes pack. | Jones Alukwe | Nicole Akinyi | 2026-11-04 | 2026-11-06 | 3 | JO-06, NI-08 | Sign-off BPF | UAT-06: sign-off blocked while residual ≠ 0 | 11.11 | Not started | 0%
JO-10 | 3 Sprint 2 | Copilot | Stock Assistant set-up + topics T1–T5 | Agent in DEV, Entra auth, STK-Knowledge library, read-only actions; topics: where is outturn, why variance, count progress, my exceptions, explain a rule. | Jones Alukwe | Nicole Akinyi | 2026-11-02 | 2026-11-06 | 5 | JO-01, DO-10 | Agent with T1–T5 | T1–T5 answer test questions correctly | 14 | Not started | 0%
MO-10 | 3 Sprint 2 | Architecture | Engine design review | Review L1–L3 order, RI taxonomy implementation and idempotency with Denis. | Moses Masibo | Denis Otieno | 2026-10-28 | 2026-10-29 | 2 | DO-10 | Review notes | Issues fixed before SIT | 4, 8.3 | Not started | 0%
MO-11 | 3 Sprint 2 | Operations | F40 health check, F41 housekeeping, Teams STK Support channel | Hourly health check; weekly archive; alert channel. | Moses Masibo |  | 2026-11-02 | 2026-11-04 | 3 | MO-09 | Flows F40–F41 | Turned-off test flow raises alert | 12.2 | Not started | 0%
MO-12 | 3 Sprint 2 | Code review | Pull-request reviews (ongoing) | Review every PR within 1 working day; enforce naming, no hard-coded values, error handling. | Moses Masibo |  | 2026-10-12 | 2026-11-06 | 19 | MO-05 | Merged PRs | No PR older than 1 day | 16.3, App. D | Not started | 0%
FR-03 | 4 SIT | Testing | Execute SIT scripts (rolling as features land) | Run scripts per area as each feature is merged; log defects; retest fixes. | Frankie Omasaja | Nicole Akinyi | 2026-10-26 | 2026-11-06 | 10 | FR-02 | SIT results + defect log | All scripts executed; 0 open Sev 1/2 | 18 | Not started | 0%
PM-31 | 4 SIT | Parallel run | Plan October month-end parallel run | Agree with Operations: counters, zones, dates (count Mon 2 – Wed 4 Nov), devices, QR labels on bays, fallback to current process. | Daphne Okwaro | Andrew Tanui, William Imo | 2026-10-26 | 2026-10-30 | 5 | PM-30 | Parallel-run plan | Ops manager agreed | 18.1 | Not started | 0%
AN-11 | 4 SIT | Parallel run | Print and fix QR labels on bays for parallel run | Generate and print labels; fix on bays with warehouse team. | Andrew Tanui | William Imo | 2026-10-29 | 2026-10-30 | 2 | AN-03 | Labels on bays | All bays in scope labelled | 10.8 | Not started | 0%
DO-15 | 4 SIT | Parallel run | Load October month-end snapshots into UAT and lock | Day 1 feeds (Sun 1 Nov) loaded and locked; stock take created. | Denis Otieno | Andrew Tanui | 2026-11-02 | 2026-11-02 | 1 | DO-08, MO-09 | Locked snapshot | Wizard pre-checks all green | 5.2 | Not started | 0%
WI-11 | 4 SIT | Parallel run | Floor support during parallel count | On the floor with counters; capture issues; quick fixes. | William Imo | Andrew Tanui | 2026-11-02 | 2026-11-04 | 3 | DO-15 | Issue list | Count completed in new app | — | Not started | 0%
DO-16 | 4 SIT | Parallel run | Run L1–L3 on October data and reconcile | Close count → L1; L2/L3 on month-end feeds; work residual with Finance/Ops. | Denis Otieno | Nicole Akinyi | 2026-11-04 | 2026-11-06 | 3 | WI-11 | Recon results | Residual explained to 0 or items listed | 4, 18.2 | Not started | 0%
NI-09 | 4 SIT | Parallel run | Parallel-run comparison report | Compare manual vs new solution: variances found, explanations, time taken (T9). | Nicole Akinyi | Daphne Okwaro | 2026-11-04 | 2026-11-06 | 3 | DO-16 | Comparison report | Shared with NKG sponsors | 18.2 T9 | Not started | 0%
DO-17 | 4 SIT | Testing | Tie-outs T1–T8 and T10 | Completeness, mapping coverage, L1, L2, L3, mass balance, repeatability, timeliness; evidence in Git /test. | Denis Otieno | Nicole Akinyi | 2026-11-02 | 2026-11-06 | 5 | DO-12 | Tie-out evidence | All = 0 difference | 18.2 | Not started | 0%
NI-10 | 4 SIT | Testing | T7 report vs source tie-out | Every Power BI total vs Dataverse query total. | Nicole Akinyi |  | 2026-11-05 | 2026-11-06 | 2 | NI-06 | T7 evidence | 0 difference | 18.2 | Not started | 0%
MO-13 | 4 SIT | Testing | Performance and security tests | Volume test (50k XBS lines, 20k count lines); SEC-01..05 role tests. | Moses Masibo | Frankie Omasaja | 2026-11-03 | 2026-11-06 | 4 | MO-08 | Test results | NFR-01/02/03 met; roles pass | 17, 18 | Not started | 0%
PM-32 | 4 SIT | Delivery | Sprint 2 review / SIT exit | Demo full flow; review SIT and parallel-run results; go/no-go for UAT. | Daphne Okwaro | All | 2026-11-06 | 2026-11-06 | 1 | FR-03 | SIT exit note | UAT entry approved | 18.4 | Not started | 0%
PM-40 | 5 Training | Training | Training plan, schedule and invites | Sessions per audience; Digitization Project Team Boardroom / Teams; attendance list. | Daphne Okwaro | Frankie Omasaja | 2026-10-29 | 2026-11-06 | 7 |  | Training schedule + invites | Invites accepted | 21 | Not started | 0%
FR-04 | 5 Training | Documentation | User guides and quick reference cards | Counter card (laminated), supervisor, Ops admin, Trade/QC/Logistics, Finance/Management guides from developer inputs. | Frankie Omasaja | William Imo, Andrew Tanui, Jones Alukwe | 2026-11-02 | 2026-11-10 | 7 | PM-32 | Guides + cards | Reviewed by PM | 21 | Not started | 0%
JO-11 | 5 Training | Copilot | Topics T6–T10 + evaluation set | Contract status, provisional status, summarise comments, draft correction note, month-end readiness; run ~30-question evaluation built with Nicole. | Jones Alukwe | Nicole Akinyi | 2026-11-09 | 2026-11-11 | 3 | JO-10, NI-09 | Agent T1–T10 + eval results | ≥ 90% correct; 100% on numbers | 14.4 | Not started | 0%
JO-12 | 5 Training | Copilot | Publish Stock Assistant to Teams (UAT) | Teams channel publish; Control Centre side pane; Help link in app. | Jones Alukwe | Moses Masibo | 2026-11-12 | 2026-11-13 | 2 | JO-11 | Published agent | Available to UAT users | 14 | Not started | 0%
WI-12 | 5 Training | Training | Train counters and supervisors (Stock Take app) | 30-min hands-on per group + card; supervisor 1 h. | William Imo | Andrew Tanui | 2026-11-09 | 2026-11-11 | 3 | FR-04 | Attendance | All named counters trained | 21 | Not started | 0%
AN-12 | 5 Training | Training | Train Operations admin and warehouse managers (Hub) | 2-h session: wizard, monitor, recounts, close, registers, third parties, admin. | Andrew Tanui |  | 2026-11-10 | 2026-11-11 | 2 | FR-04 | Attendance | Trained users can create a stock take unaided | 21 | Not started | 0%
JO-13 | 5 Training | Training | Train Trade, QC, Logistics, Finance, Management (Control Centre + Copilot) | 1.5–2 h per group: mapping, downgrade, provisional, SNI, exceptions, corrections, workspace, sign-off, Copilot. | Jones Alukwe | Nicole Akinyi, Daphne Okwaro | 2026-11-11 | 2026-11-13 | 3 | FR-04 | Attendance | ≥ 90% of named users trained | 21 | Not started | 0%
NI-11 | 5 Training | Documentation | Data dictionary | Generate from Dataverse; add business definitions. | Nicole Akinyi |  | 2026-11-09 | 2026-11-12 | 4 | DO-03 | Data dictionary | Published in STK-Knowledge | 21 | Not started | 0%
MO-14 | 5 Training | Environments | Deploy release candidate to UAT | Managed deployment; environment variables; connections; users added to groups. | Moses Masibo |  | 2026-11-12 | 2026-11-13 | 2 | PM-32 | UAT RC | Smoke test passes | 16 | Not started | 0%
FR-05 | 5 Training | Testing | UAT scripts and UAT participant packs | Scenarios UAT-01..07 per department with test data and sign-off sheet. | Frankie Omasaja | Daphne Okwaro | 2026-11-09 | 2026-11-13 | 5 | PM-32 | UAT pack | Reviewed by department leads | 18.3 | Not started | 0%
PM-50 | 6 UAT | UAT | Run UAT and daily defect triage | Kick-off Mon 16 Nov; daily 16:00 triage; track progress per department. | Daphne Okwaro | Frankie Omasaja, Moses Masibo | 2026-11-16 | 2026-11-27 | 10 | MO-14, FR-05 | UAT tracker | All scenarios executed | 18.3 | Not started | 0%
WI-13 | 6 UAT | UAT | Fix UAT defects — Stock Take app | Fix and redeploy within severity SLA. | William Imo |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started | 0%
AN-13 | 6 UAT | UAT | Fix UAT defects — Hub | Fix and redeploy within severity SLA. | Andrew Tanui |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started | 0%
JO-14 | 6 UAT | UAT | Fix UAT defects — Control Centre + Copilot | Fix and redeploy within severity SLA. | Jones Alukwe |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started | 0%
DO-18 | 6 UAT | UAT | Fix UAT defects — intake and engine | Fix and redeploy within severity SLA. | Denis Otieno |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started | 0%
NI-12 | 6 UAT | UAT | Fix UAT defects — Power BI and pack | Fix and republish. | Nicole Akinyi |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started | 0%
PM-51 | 6 UAT | UAT | UAT sign-off by department leads | Sign-off sheet per department. | Daphne Okwaro |  | 2026-11-27 | 2026-11-27 | 1 | PM-50 | Signed UAT | All departments signed | 18.4 | Not started | 0%
MO-15 | 7 Cutover | PROD | PROD readiness | Environment, DLP, groups, service account licensed, mailbox and library in PROD. | Moses Masibo | Daphne Okwaro | 2026-11-16 | 2026-11-20 | 5 | MO-03 | PROD ready | Checklist items 1 and 5 done | 20.1 | Not started | 0%
MO-16 | 7 Cutover | PROD | Deploy release candidate to PROD | Managed solutions; settings file; connections; share apps. | Moses Masibo |  | 2026-11-24 | 2026-11-24 | 1 | MO-15 | PROD RC | Smoke test passes | 20.1 | Not started | 0%
DO-19 | 7 Cutover | PROD | PROD master-data load and tie-out | Load and tie out all master data; mapping coverage = 100%. | Denis Otieno | Nicole Akinyi | 2026-11-24 | 2026-11-25 | 2 | MO-16 | PROD master data | T1/T2 pass in PROD | 20.1 | Not started | 0%
DO-20 | 7 Cutover | PROD | Switch feeds to PROD mailbox; 3 clean intake days | Owners send to PROD; monitor 25, 26, 27 Nov. | Denis Otieno |  | 2026-11-25 | 2026-11-27 | 3 | DO-19 | Clean intake log | 3 consecutive clean days | 20.1 | Not started | 0%
DO-21 | 7 Cutover | Baseline | Opening baseline calculation | Agree last reconciled position (October parallel run); record historic unexplained as RI-BASELINE. | Denis Otieno | Nicole Akinyi | 2026-11-26 | 2026-12-02 | 5 | DO-16 | Baseline workbook | Approved by Finance + Ops | 4.8, 20.3 | Not started | 0%
PM-60 | 7 Cutover | Cutover | Go / no-go meeting | Criteria: UAT signed, parallel run residual 0, feeds live, ≥ 90% trained, support rota. | Daphne Okwaro | Moses Masibo | 2026-11-27 | 2026-11-27 | 1 | PM-51, DO-20 | Go/no-go decision | Decision minuted | 20.2 | Not started | 0%
MO-17 | 7 Cutover | PROD | Final patch deploy to PROD after UAT fixes | Deploy last fixes; set legacy ITB apps read-only after first live count. | Moses Masibo |  | 2026-11-30 | 2026-11-30 | 1 | PM-60 | PROD final | Smoke test passes | 20.1 | Not started | 0%
PM-61 | 7 Cutover | Live | First live month-end count (November) in PROD | Count Tue 1 – Thu 3 Dec; whole team on call; floor support William/Andrew. | Daphne Okwaro | All | 2026-12-01 | 2026-12-03 | 3 | MO-17 | Live count | Count closed in PROD | 5.2 | Not started | 0%
DO-22 | 8 Hypercare | Live | November L1–L3 runs; drive residual to 0 | Support Finance/Ops to clear exceptions and corrections by WD7 (Wed 9 Dec). | Denis Otieno | Nicole Akinyi, Jones Alukwe | 2026-12-03 | 2026-12-09 | 5 | PM-61 | Recon results | Residual 0 at all levels | 4, 5.2 | Not started | 0%
PM-62 | 8 Hypercare | Live | First live sign-off (residual = 0 gate) | Walk signatories through BPF; pack generated and distributed. | Daphne Okwaro | Jones Alukwe | 2026-12-09 | 2026-12-09 | 1 | DO-22 | Signed period | Period locked | 11.11 | Not started | 0%
PM-63 | 8 Hypercare | Hypercare | Hypercare: daily stand-up with NKG super users | Sev1 4 h, Sev2 1 day; daily issue review. | Daphne Okwaro | All | 2026-12-01 | 2026-12-11 | 9 | MO-17 | Hypercare log | Issues closed or handed over | 20.4 | Not started | 0%
MO-18 | 8 Hypercare | Handover | Knowledge transfer to NKG IT (2 × 2 h) | ALM, flows, monitoring, support runbook. | Moses Masibo | Denis Otieno | 2026-12-07 | 2026-12-09 | 3 |  | KT attendance | NKG IT can deploy and monitor | 20.4 | Not started | 0%
DO-23 | 8 Hypercare | Handover | Runbooks for intake and engine failures | One runbook entry per failure type. | Denis Otieno |  | 2026-12-07 | 2026-12-09 | 3 |  | Runbooks | Reviewed by Moses | 17 NFR-10 | Not started | 0%
FR-06 | 8 Hypercare | Handover | As-built documentation pack | Spec as-built, admin guide, user guides, runbooks, data dictionary in STK-Knowledge. | Frankie Omasaja | Moses Masibo | 2026-12-07 | 2026-12-11 | 5 |  | Handover pack | Accepted by NKG IT | 20.4 | Not started | 0%
PM-64 | 8 Hypercare | Hypercare | Hypercare exit report | Issues, fixes, open items, recommendations. | Daphne Okwaro |  | 2026-12-11 | 2026-12-11 | 1 | PM-63 | Exit report | Sent to sponsors | 20.4 | Not started | 0%
PM-70 | 9 Acceptance | Closure | Final acceptance and project close | Formal acceptance meeting; lessons learned; budget close (USD 24,753). | Daphne Okwaro | Moses Masibo | 2026-12-14 | 2026-12-17 | 4 | PM-64 | Acceptance certificate | Signed by NKG sponsor | 19.1 | Not started | 0%
Formulas:
Work days = NETWORKDAYS([Start],[End],Holidays!$A5:A12)
Overdue? = IF(AND([Status]<>"Complete",[End]<TODAY()),"OVERDUE","")

## Next Week 12-16 Oct
Next week, day by day (Mon 12 – Fri 16 Oct)
Daily stand-up 09:00. Design walkthrough with NKG on Tue 13 Oct.
Person | Mon 12 Oct | Tue 13 Oct | Wed 14 Oct | Thu 15 Oct | Fri 16 Oct
Daphne Okwaro | Sprint 1 planning 09:30; circulate BRD/spec/mockups (PM-11); send feed request (PM-15); NKG IT licensing email (PM-16) | Create decision log; book calls with OD owners; prepare walkthrough deck | Design walkthrough with NKG (PM-13); log feedback | Chase feed samples and decisions; update BRD/spec to V1.2 | Collect sign-offs (PM-14); steering check-in; weekly status #3
Moses Masibo | ITB inventory: export solution and flows (MO-01); request environments (MO-03) | Finish ITB inventory; Git repo set-up (MO-05); ownership-transfer plan (MO-02) | Walkthrough with NKG; create publisher + solutions (MO-04) | Data-model review with Denis (MO-06); env-variable standards | Mailbox/SharePoint with NKG IT (MO-07); approve ERD
Denis Otieno | Review ITB dataflows (DO-01); support feed request | Finish dataflow review; list reusable logic | Draft intake templates (DO-02); data-model review prep | Data-model review with Moses; start Dataverse tables (DO-03) | Templates agreed with owners; continue tables
Nicole Akinyi | Prepare profiling checklist; support decision log | Profile first sample files received (NI-01) | Continue profiling; issues list to owners | Start mapping coverage analysis (NI-02) | Profiling report final; coverage first cut
William Imo | Review ITB Stock Take app (WI-01) | Finish review; start component library (WI-02) | Walkthrough demo support; finish component library | S1 Sign-in and version check (WI-03) | S2 Home; demo at stand-up
Andrew Tanui | Review ITB Stock Management app (AN-01) | Finish review; help William with component library | Walkthrough demo support; plan Hub screens | Admin screens: warehouses, grades (AN-02) | Admin: packing types, unit rules, config editor
Jones Alukwe | Copilot Studio and model-driven readiness check (JO-01) | Finish readiness note; draft site map | Walkthrough demo support (mockups 04–07, 09) | Model-driven app shell: site map (JO-02) | Master-data forms and views
Frankie Omasaja | Read BRD, spec and mockups; set up defect log | Test strategy draft (FR-01) | Walkthrough: capture questions as test cases | SIT script template per area | Test strategy approved by PM

## Gantt
Gantt (weekly)
Bars fill from Master Plan dates. Dark green = complete; light green = planned; red = overdue.
ID | Task | Owner | Start | End | Status | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14
PM-01 | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01 | Complete
PM-02 | Discovery sessions: Finance, Warehouse & Operations, Trade & QC, Logistics | Daphne Okwaro | 2026-10-02 | 2026-10-08 | Complete
PM-03 | BRD V1.1 (red = items to confirm) | Daphne Okwaro | 2026-10-05 | 2026-10-09 | Complete
PM-04 | Developer Build Specification V1.0 + screen mockups | Daphne Okwaro | 2026-10-07 | 2026-10-09 | Complete
PM-05 | System access request sent (NKG emails, Power Platform, Git, ITB environment) | Daphne Okwaro | 2026-10-05 | 2026-10-06 | Complete
PM-06 | Weekly status report #1 | Daphne Okwaro | 2026-10-02 | 2026-10-02 | Complete
PM-10 | Weekly status report #2 | Daphne Okwaro | 2026-10-09 | 2026-10-09 | In progress
PM-11 | Circulate BRD V1.1, Build Spec and mockups to NKG for review | Daphne Okwaro | 2026-10-12 | 2026-10-12 | Not started
PM-12 | Open-decision log OD1–OD9 (red items) | Daphne Okwaro | 2026-10-12 | 2026-10-16 | Not started
PM-13 | Design walkthrough with NKG (mockups + zero-variance model) | Daphne Okwaro | 2026-10-13 | 2026-10-13 | Not started
PM-14 | Obtain BRD and design sign-off | Daphne Okwaro | 2026-10-14 | 2026-10-16 | Not started
PM-15 | Formal data-feed request to XBS and Comtras/BRIC owners | Daphne Okwaro | 2026-10-12 | 2026-10-14 | Not started
PM-16 | Licensing and environment confirmation with NKG IT | Daphne Okwaro | 2026-10-12 | 2026-10-16 | Not started
MO-01 | Inventory the ITB (John Nyongesa) solution | Moses Masibo | 2026-10-12 | 2026-10-13 | Not started
MO-02 | Ownership-transfer plan for ITB apps and flows | Moses Masibo | 2026-10-13 | 2026-10-14 | Not started
MO-03 | Request/confirm DEV, UAT, PROD environments and DLP policy | Moses Masibo | 2026-10-12 | 2026-10-16 | Not started
MO-04 | Create publisher (prefix stk) and solutions in DEV | Moses Masibo | 2026-10-14 | 2026-10-15 | Not started
MO-05 | Git repository and branching | Moses Masibo | 2026-10-13 | 2026-10-15 | Not started
MO-06 | Data-model review (34 tables, keys, alternate keys) | Moses Masibo | 2026-10-14 | 2026-10-16 | Not started
NI-01 | Profile sample files from every feed | Nicole Akinyi | 2026-10-13 | 2026-10-16 | Not started
DO-01 | Review ITB dataflows and staging | Denis Otieno | 2026-10-12 | 2026-10-13 | Not started
DO-02 | Finalise intake file templates and column mappings | Denis Otieno | 2026-10-14 | 2026-10-16 | Not started
WI-01 | Review ITB Stock Take app | William Imo | 2026-10-12 | 2026-10-13 | Not started
AN-01 | Review ITB Stock Management app | Andrew Tanui | 2026-10-12 | 2026-10-13 | Not started
JO-01 | Copilot Studio and model-driven readiness check | Jones Alukwe | 2026-10-12 | 2026-10-13 | Not started
WI-02 | Shared component library (NKG theme) | William Imo | 2026-10-13 | 2026-10-14 | Not started
FR-01 | Test strategy and defect process | Frankie Omasaja | 2026-10-13 | 2026-10-16 | Not started
PM-20 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12 | Not started
MO-07 | Shared mailbox and SharePoint STK-Intake site | Moses Masibo | 2026-10-15 | 2026-10-16 | Not started
DO-03 | Create Dataverse tables in STK Core | Denis Otieno | 2026-10-15 | 2026-10-21 | Not started
DO-04 | F01 Receive intake email | Denis Otieno | 2026-10-19 | 2026-10-21 | Not started
DO-05 | F02 Validate file (V1–V7) | Denis Otieno | 2026-10-21 | 2026-10-23 | Not started
DO-06 | Dataflows to staging + F03 load | Denis Otieno | 2026-10-19 | 2026-10-23 | Not started
DO-07 | Master-data migration | Denis Otieno | 2026-10-21 | 2026-10-23 | Not started
NI-02 | Mapping coverage analysis | Nicole Akinyi | 2026-10-15 | 2026-10-21 | Not started
NI-03 | Build test data sets | Nicole Akinyi | 2026-10-19 | 2026-10-23 | Not started
WI-03 | S1 Sign-in/version check and S2 Home | William Imo | 2026-10-15 | 2026-10-16 | Not started
WI-04 | S3 My Assignments and S4 Location (QR) | William Imo | 2026-10-19 | 2026-10-22 | Not started
WI-05 | S5 Capture screen | William Imo | 2026-10-21 | 2026-10-23 | Not started
AN-02 | Admin screens | Andrew Tanui | 2026-10-15 | 2026-10-19 | Not started
AN-03 | Location generator + QR labels | Andrew Tanui | 2026-10-21 | 2026-10-22 | Not started
AN-04 | Stock take wizard (5 steps) + F10 notify | Andrew Tanui | 2026-10-21 | 2026-10-26 | Not started
JO-02 | Model-driven app shell | Jones Alukwe | 2026-10-15 | 2026-10-19 | Not started
JO-03 | Mapping BPF + F22 + versioning | Jones Alukwe | 2026-10-21 | 2026-10-23 | Not started
MO-08 | Security model build | Moses Masibo | 2026-10-19 | 2026-10-23 | Not started
MO-09 | Build and deploy pipeline DEV → UAT | Moses Masibo | 2026-10-21 | 2026-10-23 | Not started
FR-02 | Write SIT scripts | Frankie Omasaja | 2026-10-19 | 2026-10-23 | Not started
PM-21 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23 | Not started
PM-30 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26 | Not started
DO-08 | F04 missing-feed, F05 reprocess, F06 lock snapshot | Denis Otieno | 2026-10-26 | 2026-10-27 | Not started
DO-09 | Normalisation and mass balance | Denis Otieno | 2026-10-26 | 2026-10-28 | Not started
DO-10 | L1 Physical vs XBS (F30) | Denis Otieno | 2026-10-27 | 2026-10-29 | Not started
DO-11 | L2 XBS vs Comtras | Denis Otieno | 2026-10-29 | 2026-11-03 | Not started
DO-12 | L3 Baskets vs Contracts | Denis Otieno | 2026-11-02 | 2026-11-04 | Not started
DO-13 | F20 daily rules EX05–EX20 + upsert child flow | Denis Otieno | 2026-10-28 | 2026-11-04 | Not started
DO-14 | F23 provisional auto-match, F28 correction posting check | Denis Otieno | 2026-11-03 | 2026-11-05 | Not started
NI-04 | Power BI model | Nicole Akinyi | 2026-10-26 | 2026-10-28 | Not started
NI-05 | DAX measures | Nicole Akinyi | 2026-10-28 | 2026-10-29 | Not started
NI-06 | Eight report pages | Nicole Akinyi | 2026-10-29 | 2026-11-04 | Not started
NI-07 | RLS, workspace app, embed | Nicole Akinyi | 2026-11-04 | 2026-11-05 | Not started
NI-08 | Month-end pack template (F32) | Nicole Akinyi | 2026-11-03 | 2026-11-06 | Not started
WI-06 | S6 Location summary and close; F11 bulk submit | William Imo | 2026-10-26 | 2026-10-27 | Not started
WI-07 | Offline queue and sync (S9) | William Imo | 2026-10-27 | 2026-10-29 | Not started
WI-08 | Smart warnings + F12 not-in-list alert | William Imo | 2026-10-28 | 2026-10-30 | Not started
WI-09 | S7 Recount (double-blind), S8 100% issue/receive, S10 Help | William Imo | 2026-10-29 | 2026-11-02 | Not started
WI-10 | Device and floor testing | William Imo | 2026-11-03 | 2026-11-05 | Not started
AN-05 | Assignments board and auto-balance | Andrew Tanui | 2026-10-26 | 2026-10-27 | Not started
AN-06 | Live monitor | Andrew Tanui | 2026-10-27 | 2026-10-29 | Not started
AN-07 | F13 location variance check, recount and unidentified queues | Andrew Tanui | 2026-10-29 | 2026-10-30 | Not started
AN-08 | Variance review, manual approvals, close count + F14 | Andrew Tanui | 2026-11-02 | 2026-11-03 | Not started
AN-09 | Third-party confirmations + F15 | Andrew Tanui | 2026-11-04 | 2026-11-05 | Not started
AN-10 | Registers + F24, Imports & load log, Audit | Andrew Tanui | 2026-11-05 | 2026-11-06 | Not started
JO-04 | Contracts lineage + F26, provisional pipeline views | Jones Alukwe | 2026-10-26 | 2026-10-27 | Not started
JO-05 | Exception register + F21 notifications | Jones Alukwe | 2026-10-27 | 2026-10-29 | Not started
JO-06 | Reconciliation workspace (custom page) | Jones Alukwe | 2026-10-28 | 2026-11-03 | Not started
JO-07 | Corrections + approval matrix + F27 batch | Jones Alukwe | 2026-11-02 | 2026-11-03 | Not started
JO-08 | Downgrade worksheet + F25; SNI/shorts views; feedback log | Jones Alukwe | 2026-11-03 | 2026-11-04 | Not started
JO-09 | Sign-off BPF + F31 gate/lock + F32 trigger | Jones Alukwe | 2026-11-04 | 2026-11-06 | Not started
JO-10 | Stock Assistant set-up + topics T1–T5 | Jones Alukwe | 2026-11-02 | 2026-11-06 | Not started
MO-10 | Engine design review | Moses Masibo | 2026-10-28 | 2026-10-29 | Not started
MO-11 | F40 health check, F41 housekeeping, Teams STK Support channel | Moses Masibo | 2026-11-02 | 2026-11-04 | Not started
MO-12 | Pull-request reviews (ongoing) | Moses Masibo | 2026-10-12 | 2026-11-06 | Not started
FR-03 | Execute SIT scripts (rolling as features land) | Frankie Omasaja | 2026-10-26 | 2026-11-06 | Not started
PM-31 | Plan October month-end parallel run | Daphne Okwaro | 2026-10-26 | 2026-10-30 | Not started
AN-11 | Print and fix QR labels on bays for parallel run | Andrew Tanui | 2026-10-29 | 2026-10-30 | Not started
DO-15 | Load October month-end snapshots into UAT and lock | Denis Otieno | 2026-11-02 | 2026-11-02 | Not started
WI-11 | Floor support during parallel count | William Imo | 2026-11-02 | 2026-11-04 | Not started
DO-16 | Run L1–L3 on October data and reconcile | Denis Otieno | 2026-11-04 | 2026-11-06 | Not started
NI-09 | Parallel-run comparison report | Nicole Akinyi | 2026-11-04 | 2026-11-06 | Not started
DO-17 | Tie-outs T1–T8 and T10 | Denis Otieno | 2026-11-02 | 2026-11-06 | Not started
NI-10 | T7 report vs source tie-out | Nicole Akinyi | 2026-11-05 | 2026-11-06 | Not started
MO-13 | Performance and security tests | Moses Masibo | 2026-11-03 | 2026-11-06 | Not started
PM-32 | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06 | Not started
PM-40 | Training plan, schedule and invites | Daphne Okwaro | 2026-10-29 | 2026-11-06 | Not started
FR-04 | User guides and quick reference cards | Frankie Omasaja | 2026-11-02 | 2026-11-10 | Not started
JO-11 | Topics T6–T10 + evaluation set | Jones Alukwe | 2026-11-09 | 2026-11-11 | Not started
JO-12 | Publish Stock Assistant to Teams (UAT) | Jones Alukwe | 2026-11-12 | 2026-11-13 | Not started
WI-12 | Train counters and supervisors (Stock Take app) | William Imo | 2026-11-09 | 2026-11-11 | Not started
AN-12 | Train Operations admin and warehouse managers (Hub) | Andrew Tanui | 2026-11-10 | 2026-11-11 | Not started
JO-13 | Train Trade, QC, Logistics, Finance, Management (Control Centre + Copilot) | Jones Alukwe | 2026-11-11 | 2026-11-13 | Not started
NI-11 | Data dictionary | Nicole Akinyi | 2026-11-09 | 2026-11-12 | Not started
MO-14 | Deploy release candidate to UAT | Moses Masibo | 2026-11-12 | 2026-11-13 | Not started
FR-05 | UAT scripts and UAT participant packs | Frankie Omasaja | 2026-11-09 | 2026-11-13 | Not started
PM-50 | Run UAT and daily defect triage | Daphne Okwaro | 2026-11-16 | 2026-11-27 | Not started
WI-13 | Fix UAT defects — Stock Take app | William Imo | 2026-11-16 | 2026-11-26 | Not started
AN-13 | Fix UAT defects — Hub | Andrew Tanui | 2026-11-16 | 2026-11-26 | Not started
JO-14 | Fix UAT defects — Control Centre + Copilot | Jones Alukwe | 2026-11-16 | 2026-11-26 | Not started
DO-18 | Fix UAT defects — intake and engine | Denis Otieno | 2026-11-16 | 2026-11-26 | Not started
NI-12 | Fix UAT defects — Power BI and pack | Nicole Akinyi | 2026-11-16 | 2026-11-26 | Not started
PM-51 | UAT sign-off by department leads | Daphne Okwaro | 2026-11-27 | 2026-11-27 | Not started
MO-15 | PROD readiness | Moses Masibo | 2026-11-16 | 2026-11-20 | Not started
MO-16 | Deploy release candidate to PROD | Moses Masibo | 2026-11-24 | 2026-11-24 | Not started
DO-19 | PROD master-data load and tie-out | Denis Otieno | 2026-11-24 | 2026-11-25 | Not started
DO-20 | Switch feeds to PROD mailbox; 3 clean intake days | Denis Otieno | 2026-11-25 | 2026-11-27 | Not started
DO-21 | Opening baseline calculation | Denis Otieno | 2026-11-26 | 2026-12-02 | Not started
PM-60 | Go / no-go meeting | Daphne Okwaro | 2026-11-27 | 2026-11-27 | Not started
MO-17 | Final patch deploy to PROD after UAT fixes | Moses Masibo | 2026-11-30 | 2026-11-30 | Not started
PM-61 | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03 | Not started
DO-22 | November L1–L3 runs; drive residual to 0 | Denis Otieno | 2026-12-03 | 2026-12-09 | Not started
PM-62 | First live sign-off (residual = 0 gate) | Daphne Okwaro | 2026-12-09 | 2026-12-09 | Not started
PM-63 | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11 | Not started
MO-18 | Knowledge transfer to NKG IT (2 × 2 h) | Moses Masibo | 2026-12-07 | 2026-12-09 | Not started
DO-23 | Runbooks for intake and engine failures | Denis Otieno | 2026-12-07 | 2026-12-09 | Not started
FR-06 | As-built documentation pack | Frankie Omasaja | 2026-12-07 | 2026-12-11 | Not started
PM-64 | Hypercare exit report | Daphne Okwaro | 2026-12-11 | 2026-12-11 | Not started
PM-70 | Final acceptance and project close | Daphne Okwaro | 2026-12-14 | 2026-12-17 | Not started

## Milestones
Milestones
Days to go counts calendar days from today.
# | Milestone | Date | Owner | Status | Days to go
1 | Discovery complete | 2026-10-09 | Daphne Okwaro | Complete | —
2 | BRD and design signed off | 2026-10-16 | Daphne Okwaro | Planned | 7
3 | All open decisions OD1–OD9 closed | 2026-10-23 | Daphne Okwaro | Planned | 14
4 | Feeds arriving automatically in DEV mailbox | 2026-10-21 | Denis Otieno | Planned | 12
5 | Sprint 1 demo | 2026-10-23 | Daphne Okwaro | Planned | 14
6 | October parallel count (count 2–4 Nov) | 2026-11-04 | Daphne Okwaro | Planned | 26
7 | Sprint 2 demo / SIT exit | 2026-11-06 | Daphne Okwaro | Planned | 28
8 | Training complete | 2026-11-13 | Daphne Okwaro | Planned | 35
9 | UAT signed off + go/no-go | 2026-11-27 | Daphne Okwaro | Planned | 49
10 | PROD final deployment | 2026-11-30 | Moses Masibo | Planned | 52
11 | First live count closed (November) | 2026-12-03 | Daphne Okwaro | Planned | 55
12 | First sign-off with residual = 0 (WD7) | 2026-12-09 | Daphne Okwaro | Planned | 61
13 | Hypercare exit | 2026-12-11 | Daphne Okwaro | Planned | 63
14 | Final acceptance / go-live (business case) | 2026-12-17 | Daphne Okwaro | Planned | 69
Formulas:
Days to go = IF([Status]="Complete","—",[Date]-TODAY())

## NKG Actions
What we need from NKG
Send this list with the weekly status. Late items push the dependent task.
ID | What we need | NKG owner | Needed by | Blocks our task | Our task owner | Status | Days late
NK-01 | Review BRD V1.1, spec and mockups; send comments | Carol, Maina, Mathew, Denis Koech, department leads | 2026-10-14 | PM-11 | Daphne Okwaro | Requested
NK-02 | OD1 Cut-off rule (last 3 days posting window vs Day 1 download) | Finance + Operations | 2026-10-16 | PM-12 | Daphne Okwaro | Requested
NK-03 | OD2 Unit rule for pockets and lights | Warehouse (Luis Brian) | 2026-10-16 | PM-12 | Daphne Okwaro | Requested
NK-04 | OD3 Low Grade posting method in Comtras/BRIC | Finance + Trade | 2026-10-16 | PM-12 | Daphne Okwaro | Requested
NK-05 | OD4 Where provisional stock is shown | Trade + Finance | 2026-10-16 | PM-12 | Daphne Okwaro | Requested
NK-06 | OD5 Count tolerance (proposed 0 eq60) | Operations | 2026-10-16 | PM-12 | Daphne Okwaro | Requested
NK-07 | OD6 Write-off approval thresholds | Finance | 2026-10-23 | PM-12 | Daphne Okwaro | Requested
NK-08 | OD7 Sign-off order and signatories | Finance | 2026-10-23 | PM-12 | Daphne Okwaro | Requested
NK-09 | OD8 Copilot Studio approval and licensing | NKG IT | 2026-10-23 | PM-12 | Daphne Okwaro | Requested
NK-10 | OD9 Licences (Premium), service account, DEV/UAT/PROD environments | NKG IT | 2026-10-16 | PM-16 | Daphne Okwaro | Requested
NK-11 | Sample files for every feed (XBS stock & movements, 526, 537, contracts, SNI, provisional, third-party) | XBS and Comtras/BRIC owners, Logistics | 2026-10-14 | PM-15 | Daphne Okwaro | Requested
NK-12 | Scheduled daily emails of feeds to the shared mailbox at 07:00 | XBS and Comtras/BRIC owners | 2026-10-21 | DO-04 | Denis Otieno | Requested
NK-13 | Create shared mailbox and SharePoint site | NKG IT | 2026-10-16 | MO-07 | Moses Masibo | Requested
NK-14 | Transfer ITB flow/app ownership from external account | NKG IT | 2026-10-23 | MO-02 | Moses Masibo | Requested
NK-15 | Trade/QC propose mappings for unmapped outturns | Trade + QC (Judy Murimi) | 2026-10-28 | NI-02 | Nicole Akinyi | Requested
NK-16 | Name counters, supervisors and devices for parallel run | Operations / Warehouse | 2026-10-28 | PM-31 | Daphne Okwaro | Requested
NK-17 | Third-party warehouse contacts (all 5) | Logistics | 2026-10-23 | AN-09 | Andrew Tanui | Requested
NK-18 | Name UAT participants per department | Department leads | 2026-11-06 | FR-05 | Frankie Omasaja | Requested
NK-19 | Attend training sessions | All named users | 2026-11-13 | PM-40 | Daphne Okwaro | Requested
NK-20 | Approve opening baseline | Finance + Operations | 2026-12-02 | DO-21 | Denis Otieno | Requested
Formulas:
Days late = IF(AND([Status]<>"Received",TODAY()>[Needed by]),TODAY()-[Needed by],"")

## Meetings & Rhythm
Meetings and working rhythm
Location: Digitization Project Team Boardroom / Microsoft Teams Meeting
Meeting / routine | When | Who | Organiser | Period | Notes
Daily stand-up (15 min) | Every working day 09:00 | All team | Daphne Okwaro | 12 Oct – 11 Dec | Yesterday / today / blockers; update the plan statuses
Weekly status report to NKG | Every Friday | NKG distribution list | Daphne Okwaro | 9 Oct – 11 Dec | Word + email; RAG, progress, next week, decisions needed
Decision chase (OD1–OD9) | Daily until closed | Decision owners | Daphne Okwaro | 12 – 23 Oct | One message per open decision
RAID log update | Every Friday | Team | Daphne Okwaro | 9 Oct – 11 Dec | Risks, assumptions, issues, dependencies
PR code review | Within 1 working day of each PR | Developers | Moses Masibo | 12 Oct – 11 Dec | Naming, no hard-coded values, error handling
Sprint planning | Mon 12 Oct, Mon 26 Oct | All team | Daphne Okwaro | — | 1 hour
Sprint review / demo to NKG | Fri 23 Oct, Fri 6 Nov | NKG + team | Daphne Okwaro | — | 1 hour, Teams
Steering check-in with sponsor | Fri 16 Oct, 30 Oct, 13 Nov, 27 Nov, 11 Dec | NKG sponsors | Daphne Okwaro | — | 30 min
UAT defect triage | Daily 16:00 | Team + UAT leads | Daphne Okwaro | 16 – 27 Nov | Severity, owner, fix date
Budget tracking | Last Friday of month | Pathways | Daphne Okwaro | Oct – Dec | Against USD 24,753

## Daphne
Daphne Okwaro — Project Manager / Data Analytics Lead
Owns: Plan, NKG decisions, access, stakeholder management, status reporting, SIT/UAT/training/cutover coordination. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Kick-off with NKG; walk the warehouse floor; observe stacking, rows A–G / sections 1–14, bag tags, pockets, lights. | All | 2026-10-01 | 2026-10-01 | 1 |  | Kick-off notes | Held with NKG stakeholders | — | Complete
PM-06 | 0 Discovery | Weekly status report #1 | Status email (Word + HTML) to NKG. |  | 2026-10-02 | 2026-10-02 | 1 |  | Status report | Sent | — | Complete
PM-02 | 0 Discovery | Discovery sessions: Finance, Warehouse & Operations, Trade & QC, Logistics | Run four sessions; record and transcribe; capture process, pain points, reports, data owners. | Moses Masibo, Denis Otieno, Nicole Akinyi | 2026-10-02 | 2026-10-08 | 5 | PM-01 | Recordings + notes | All four sessions held and transcribed | BRD | Complete
PM-05 | 0 Discovery | System access request sent (NKG emails, Power Platform, Git, ITB environment) | Request NKG accounts for all 8 team members, environment maker access, Git, legacy ITB environment. | Moses Masibo | 2026-10-05 | 2026-10-06 | 2 |  | Access request email | Sent; ITB environment access received | 16 | Complete
PM-03 | 0 Discovery | BRD V1.1 (red = items to confirm) | Update the BRD from all recordings; mark unconfirmed items in red. | Nicole Akinyi | 2026-10-05 | 2026-10-09 | 5 | PM-02 | STOCKTAKE_BRD_V1.1.docx | Issued to team | BRD | Complete
PM-04 | 0 Discovery | Developer Build Specification V1.0 + screen mockups | Write the build specification (Sections 1–22 + appendices) and 10 screen mockups. | Moses Masibo | 2026-10-07 | 2026-10-09 | 3 | PM-03 | Spec V1.0 + mockups PDF | Issued to team | All | Complete
PM-10 | 1 Design | Weekly status report #2 | Progress: discovery complete, BRD V1.1, build spec, mockups; next week: design sign-off, decisions OD1–OD9, sprint 1 start. |  | 2026-10-09 | 2026-10-09 | 1 | PM-04 | Status report | Sent to NKG distribution list | — | In progress
PM-11 | 1 Design | Circulate BRD V1.1, Build Spec and mockups to NKG for review | Email to Carol, Maina, Mathew, Denis Koech, department leads; ask for written comments by Wed 14 Oct; attach mockups PDF. |  | 2026-10-12 | 2026-10-12 | 1 | PM-04 | Review email | Sent; every reviewer acknowledged | — | Not started
PM-20 | 2 Sprint 1 | Sprint 1 planning | Assign Sprint 1 stories; confirm capacity (Mashujaa Day Tue 20 Oct is a public holiday). | All | 2026-10-12 | 2026-10-12 | 1 |  | Sprint 1 board | Every story has owner and estimate | 19 | Not started
PM-15 | 1 Design | Formal data-feed request to XBS and Comtras/BRIC owners | Request: (1) sample files for every feed S1–S15 by 14 Oct; (2) scheduled daily email to shared mailbox at 07:00 with subject STK¦<SOURCE>¦<YYYYMMDD>¦<HHMM>; (3) named backup sender. | Denis Otieno | 2026-10-12 | 2026-10-14 | 3 |  | Feed request email + owner list | Every feed has a named owner and a start date | 7.1–7.2 | Not started
PM-12 | 1 Design | Open-decision log OD1–OD9 (red items) | Create decision log (decision, options, recommendation, owner, needed-by). Book 30-min calls per owner. Chase daily until closed. OD1 cut-off rule; OD2 unit rule (pocket, lights); OD3 Low Grade posting; OD4 provisional stock location; OD5 count tolerance; OD6 write-off thresholds; OD7 sign-off order; OD8 Copilot approval; OD9 licensing/environments. | Moses Masibo | 2026-10-12 | 2026-10-16 | 5 | PM-11 | Decision log | OD1–OD5 and OD9 closed by 16 Oct; OD6–OD8 by 23 Oct | 22.3 | Not started
PM-16 | 1 Design | Licensing and environment confirmation with NKG IT | Confirm Power Apps Premium for Hub/Control Centre users, service account stk.svc, shared mailbox, DEV/UAT/PROD Dataverse environments, Copilot Studio availability. | Moses Masibo | 2026-10-12 | 2026-10-16 | 5 |  | Confirmation email from NKG IT | Licences and environments confirmed in writing | 15, 16 | Not started
PM-13 | 1 Design | Design walkthrough with NKG (mockups + zero-variance model) | 2-hour session, Digitization Project Team Boardroom / Teams. Demo mockups screen by screen; explain residual = 0 gate; collect feedback. | Moses Masibo, William Imo, Andrew Tanui, Jones Alukwe | 2026-10-13 | 2026-10-13 | 1 | PM-11 | Feedback list | Feedback logged and triaged into backlog | 3, 4, 9–14 | Not started
PM-14 | 1 Design | Obtain BRD and design sign-off | Update BRD/spec for walkthrough feedback (V1.2); obtain written sign-off from the approval table. | Moses Masibo | 2026-10-14 | 2026-10-16 | 3 | PM-13, PM-12 | Signed BRD V1.2 + Spec V1.1 | Signatures/approval emails received | Doc control | Not started
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Demo intake, master data, Stock Take app capture, wizard, mapping BPF. | All | 2026-10-23 | 2026-10-23 | 1 |  | Demo + feedback | NKG feedback logged | 19 | Not started
PM-30 | 3 Sprint 2 | Sprint 2 planning | Carry-over from Sprint 1; confirm parallel-run plan. | All | 2026-10-26 | 2026-10-26 | 1 | PM-21 | Sprint 2 board | Stories assigned | 19 | Not started
PM-31 | 4 SIT | Plan October month-end parallel run | Agree with Operations: counters, zones, dates (count Mon 2 – Wed 4 Nov), devices, QR labels on bays, fallback to current process. | Andrew Tanui, William Imo | 2026-10-26 | 2026-10-30 | 5 | PM-30 | Parallel-run plan | Ops manager agreed | 18.1 | Not started
PM-40 | 5 Training | Training plan, schedule and invites | Sessions per audience; Digitization Project Team Boardroom / Teams; attendance list. | Frankie Omasaja | 2026-10-29 | 2026-11-06 | 7 |  | Training schedule + invites | Invites accepted | 21 | Not started
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Demo full flow; review SIT and parallel-run results; go/no-go for UAT. | All | 2026-11-06 | 2026-11-06 | 1 | FR-03 | SIT exit note | UAT entry approved | 18.4 | Not started
PM-50 | 6 UAT | Run UAT and daily defect triage | Kick-off Mon 16 Nov; daily 16:00 triage; track progress per department. | Frankie Omasaja, Moses Masibo | 2026-11-16 | 2026-11-27 | 10 | MO-14, FR-05 | UAT tracker | All scenarios executed | 18.3 | Not started
PM-51 | 6 UAT | UAT sign-off by department leads | Sign-off sheet per department. |  | 2026-11-27 | 2026-11-27 | 1 | PM-50 | Signed UAT | All departments signed | 18.4 | Not started
PM-60 | 7 Cutover | Go / no-go meeting | Criteria: UAT signed, parallel run residual 0, feeds live, ≥ 90% trained, support rota. | Moses Masibo | 2026-11-27 | 2026-11-27 | 1 | PM-51, DO-20 | Go/no-go decision | Decision minuted | 20.2 | Not started
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Count Tue 1 – Thu 3 Dec; whole team on call; floor support William/Andrew. | All | 2026-12-01 | 2026-12-03 | 3 | MO-17 | Live count | Count closed in PROD | 5.2 | Not started
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Sev1 4 h, Sev2 1 day; daily issue review. | All | 2026-12-01 | 2026-12-11 | 9 | MO-17 | Hypercare log | Issues closed or handed over | 20.4 | Not started
PM-62 | 8 Hypercare | First live sign-off (residual = 0 gate) | Walk signatories through BPF; pack generated and distributed. | Jones Alukwe | 2026-12-09 | 2026-12-09 | 1 | DO-22 | Signed period | Period locked | 11.11 | Not started
PM-64 | 8 Hypercare | Hypercare exit report | Issues, fixes, open items, recommendations. |  | 2026-12-11 | 2026-12-11 | 1 | PM-63 | Exit report | Sent to sponsors | 20.4 | Not started
PM-70 | 9 Acceptance | Final acceptance and project close | Formal acceptance meeting; lessons learned; budget close (USD 24,753). | Moses Masibo | 2026-12-14 | 2026-12-17 | 4 | PM-64 | Acceptance certificate | Signed by NKG sponsor | 19.1 | Not started
Tasks where Daphne is supporting
ID | Phase | Task | Owner | Start | End
MO-03 | 1 Design | Request/confirm DEV, UAT, PROD environments and DLP policy | Moses Masibo | 2026-10-12 | 2026-10-16
FR-01 | 1 Design | Test strategy and defect process | Frankie Omasaja | 2026-10-13 | 2026-10-16
NI-09 | 4 SIT | Parallel-run comparison report | Nicole Akinyi | 2026-11-04 | 2026-11-06
FR-05 | 5 Training | UAT scripts and UAT participant packs | Frankie Omasaja | 2026-11-09 | 2026-11-13
JO-13 | 5 Training | Train Trade, QC, Logistics, Finance, Management (Control Centre + Copilot) | Jones Alukwe | 2026-11-11 | 2026-11-13
MO-15 | 7 Cutover | PROD readiness | Moses Masibo | 2026-11-16 | 2026-11-20

## Moses
Moses Masibo — Solution Architect
Owns: Environments, solutions, ALM and Git, security model, data-model and engine design review, code review, PROD readiness. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
MO-01 | 1 Design | Inventory the ITB (John Nyongesa) solution | Export managed solution "NKG Stock Solution" and all flows; list every app, flow, dataflow, table, SharePoint list, connection and owner; note what to keep/rebuild/retire. | Denis Otieno | 2026-10-12 | 2026-10-13 | 2 | PM-05 | ITB inventory sheet + exported zip in Git /legacy | Inventory reviewed with team | 2, 16.4 | Not started
MO-03 | 1 Design | Request/confirm DEV, UAT, PROD environments and DLP policy | Dataverse in each; DLP Business group: Dataverse, SharePoint, Outlook, Teams, Approvals, Power BI; block consumer connectors. | Daphne Okwaro | 2026-10-12 | 2026-10-16 | 5 | PM-16 | Environments live | Team can open DEV as makers | 16.1, 15.2 | Not started
MO-12 | 3 Sprint 2 | Pull-request reviews (ongoing) | Review every PR within 1 working day; enforce naming, no hard-coded values, error handling. |  | 2026-10-12 | 2026-11-06 | 19 | MO-05 | Merged PRs | No PR older than 1 day | 16.3, App. D | Not started
MO-02 | 1 Design | Ownership-transfer plan for ITB apps and flows | Plan transfer of flows/apps from the external account to stk.svc so nothing stops when the external account is removed; agree date with NKG IT. |  | 2026-10-13 | 2026-10-14 | 2 | MO-01 | Transfer plan | NKG IT agreed date | 16.4 | Not started
MO-05 | 1 Design | Git repository and branching | Create repo (/solutions, /powerbi, /docs, /test, /legacy); main/develop/feature branches; PR rule (Moses reviews); access for all 8. |  | 2026-10-13 | 2026-10-15 | 3 | PM-05 | Git repo | First commit by every developer | 16.3 | Not started
MO-04 | 1 Design | Create publisher (prefix stk) and solutions in DEV | STK Core, STK Apps, STK Automation, STK Copilot; environment-variable and connection-reference standards. |  | 2026-10-14 | 2026-10-15 | 2 | MO-03 | Solutions in DEV | All devs building inside solutions | 16.2, App. D | Not started
MO-06 | 1 Design | Data-model review (34 tables, keys, alternate keys) | Review with Denis: columns, choice sets, relationships, alternate keys (stk_localid, rule+key), audit settings. | Denis Otieno | 2026-10-14 | 2026-10-16 | 3 | MO-04 | Approved ERD | Signed off by Moses | 6 | Not started
MO-07 | 2 Sprint 1 | Shared mailbox and SharePoint STK-Intake site | With NKG IT: create mailbox stocktake.data@nkg.coffee; library STK-Intake with Incoming/Rejected/Processed/Templates; permissions for stk.svc. | Denis Otieno | 2026-10-15 | 2026-10-16 | 2 | PM-16 | Mailbox + library | Test email lands and is readable by flow | 7.1 | Not started
MO-08 | 2 Sprint 1 | Security model build | Entra groups SG-STK-<Role>; 10 Dataverse roles; team mapping; field security (expected qty hidden from Counter, approvals, config). |  | 2026-10-19 | 2026-10-23 | 4 | DO-03 | Roles + groups | Role test: counter cannot read expected qty | 15 | Not started
MO-09 | 2 Sprint 1 | Build and deploy pipeline DEV → UAT | pac CLI export/unpack/commit; managed build; deployment settings per environment. |  | 2026-10-21 | 2026-10-23 | 3 | MO-05 | Pipeline | First managed deploy to UAT succeeds | 16.3 | Not started
MO-10 | 3 Sprint 2 | Engine design review | Review L1–L3 order, RI taxonomy implementation and idempotency with Denis. | Denis Otieno | 2026-10-28 | 2026-10-29 | 2 | DO-10 | Review notes | Issues fixed before SIT | 4, 8.3 | Not started
MO-11 | 3 Sprint 2 | F40 health check, F41 housekeeping, Teams STK Support channel | Hourly health check; weekly archive; alert channel. |  | 2026-11-02 | 2026-11-04 | 3 | MO-09 | Flows F40–F41 | Turned-off test flow raises alert | 12.2 | Not started
MO-13 | 4 SIT | Performance and security tests | Volume test (50k XBS lines, 20k count lines); SEC-01..05 role tests. | Frankie Omasaja | 2026-11-03 | 2026-11-06 | 4 | MO-08 | Test results | NFR-01/02/03 met; roles pass | 17, 18 | Not started
MO-14 | 5 Training | Deploy release candidate to UAT | Managed deployment; environment variables; connections; users added to groups. |  | 2026-11-12 | 2026-11-13 | 2 | PM-32 | UAT RC | Smoke test passes | 16 | Not started
MO-15 | 7 Cutover | PROD readiness | Environment, DLP, groups, service account licensed, mailbox and library in PROD. | Daphne Okwaro | 2026-11-16 | 2026-11-20 | 5 | MO-03 | PROD ready | Checklist items 1 and 5 done | 20.1 | Not started
MO-16 | 7 Cutover | Deploy release candidate to PROD | Managed solutions; settings file; connections; share apps. |  | 2026-11-24 | 2026-11-24 | 1 | MO-15 | PROD RC | Smoke test passes | 20.1 | Not started
MO-17 | 7 Cutover | Final patch deploy to PROD after UAT fixes | Deploy last fixes; set legacy ITB apps read-only after first live count. |  | 2026-11-30 | 2026-11-30 | 1 | PM-60 | PROD final | Smoke test passes | 20.1 | Not started
MO-18 | 8 Hypercare | Knowledge transfer to NKG IT (2 × 2 h) | ALM, flows, monitoring, support runbook. | Denis Otieno | 2026-12-07 | 2026-12-09 | 3 |  | KT attendance | NKG IT can deploy and monitor | 20.4 | Not started
Tasks where Moses is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-02 | 0 Discovery | Discovery sessions: Finance, Warehouse & Operations, Trade & QC, Logistics | Daphne Okwaro | 2026-10-02 | 2026-10-08
PM-05 | 0 Discovery | System access request sent (NKG emails, Power Platform, Git, ITB environment) | Daphne Okwaro | 2026-10-05 | 2026-10-06
PM-04 | 0 Discovery | Developer Build Specification V1.0 + screen mockups | Daphne Okwaro | 2026-10-07 | 2026-10-09
PM-12 | 1 Design | Open-decision log OD1–OD9 (red items) | Daphne Okwaro | 2026-10-12 | 2026-10-16
PM-16 | 1 Design | Licensing and environment confirmation with NKG IT | Daphne Okwaro | 2026-10-12 | 2026-10-16
DO-01 | 1 Design | Review ITB dataflows and staging | Denis Otieno | 2026-10-12 | 2026-10-13
JO-01 | 1 Design | Copilot Studio and model-driven readiness check | Jones Alukwe | 2026-10-12 | 2026-10-13
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
PM-13 | 1 Design | Design walkthrough with NKG (mockups + zero-variance model) | Daphne Okwaro | 2026-10-13 | 2026-10-13
PM-14 | 1 Design | Obtain BRD and design sign-off | Daphne Okwaro | 2026-10-14 | 2026-10-16
DO-03 | 2 Sprint 1 | Create Dataverse tables in STK Core | Denis Otieno | 2026-10-15 | 2026-10-21
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
DO-09 | 3 Sprint 2 | Normalisation and mass balance | Denis Otieno | 2026-10-26 | 2026-10-28
WI-07 | 3 Sprint 2 | Offline queue and sync (S9) | William Imo | 2026-10-27 | 2026-10-29
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
JO-12 | 5 Training | Publish Stock Assistant to Teams (UAT) | Jones Alukwe | 2026-11-12 | 2026-11-13
PM-50 | 6 UAT | Run UAT and daily defect triage | Daphne Okwaro | 2026-11-16 | 2026-11-27
PM-60 | 7 Cutover | Go / no-go meeting | Daphne Okwaro | 2026-11-27 | 2026-11-27
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11
FR-06 | 8 Hypercare | As-built documentation pack | Frankie Omasaja | 2026-12-07 | 2026-12-11
PM-70 | 9 Acceptance | Final acceptance and project close | Daphne Okwaro | 2026-12-14 | 2026-12-17

## Denis
Denis Otieno — Data Engineer
Owns: Email intake, validation, dataflows, Dataverse tables, master-data migration, reconciliation engine L1–L3, rules, tie-outs. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
DO-01 | 1 Design | Review ITB dataflows and staging | Understand current dataflows → Dataverse staging → SharePoint lists; note reusable logic and known failures. | Moses Masibo | 2026-10-12 | 2026-10-13 | 2 | PM-05 | Notes in Git /docs | Reviewed with Moses | 2 | Not started
DO-02 | 1 Design | Finalise intake file templates and column mappings | Agree exact column names per feed with owners; publish templates in STK-Intake/Templates. | Nicole Akinyi | 2026-10-14 | 2026-10-16 | 3 | NI-01 | Templates S1–S15 | Owners confirm they can produce them | App. E | Not started
DO-03 | 2 Sprint 1 | Create Dataverse tables in STK Core | Build 34 stk_ tables with columns, choices, alternate keys, relationships, auditing; stk_config seeded with keys. | Moses Masibo | 2026-10-15 | 2026-10-21 | 4 | MO-06 | Tables in DEV | ERD = DEV schema; solution exported to Git | 6 | Not started
DO-04 | 2 Sprint 1 | F01 Receive intake email | Trigger on shared mailbox; parse subject; sender allow-list; save attachment as <SOURCE>_<YYYYMMDD>_<HHMM>.<ext>; log to stk_loadlog. |  | 2026-10-19 | 2026-10-21 | 2 | MO-07, DO-03 | Flow F01 | 10 test emails processed correctly, bad sender rejected | 12.2 | Not started
DO-06 | 2 Sprint 1 | Dataflows to staging + F03 load | One dataflow per source (XBS stock, XBS movements, 526, 537, contracts, SNI, provisional, third-party); F03 refresh, poll, snapshot header, row-count check. |  | 2026-10-19 | 2026-10-23 | 4 | DO-03 | Dataflows + F03 | T1 completeness passes for every sample file | 7, 12.2 | Not started
DO-05 | 2 Sprint 1 | F02 Validate file (V1–V7) | Columns, types, dates, row counts, duplicates, control totals, period; move to Rejected + reply with reason, or Processed + trigger load. | Nicole Akinyi | 2026-10-21 | 2026-10-23 | 3 | DO-04 | Flow F02 | Each V-rule has a failing test file that is rejected with the right reason | 7.3 | Not started
DO-07 | 2 Sprint 1 | Master-data migration | Load warehouses, locations, zones, grades, quality codes, packing types, secondary/primary baskets, contracts, mappings from ITB lists and Comtras. | Nicole Akinyi | 2026-10-21 | 2026-10-23 | 3 | DO-03 | Master data in DEV | Counts tie to sources; T2 coverage report produced | 7.5 | Not started
DO-08 | 3 Sprint 2 | F04 missing-feed, F05 reprocess, F06 lock snapshot | F04 08:00 check → EX20; F05 Hub button; F06 locks month-end snapshot. |  | 2026-10-26 | 2026-10-27 | 2 | DO-06 | Flows F04–F06 | Missing test feed raises EX20 | 12.2 | Not started
DO-09 | 3 Sprint 2 | Normalisation and mass balance | Convert all positions to kg/eq60 with unit rules; opening + receipts − issues ± adjustments = closing per outturn. | Moses Masibo | 2026-10-26 | 2026-10-28 | 3 | DO-07 | Engine step 1 | T6 passes on test data | 4.2–4.3 | Not started
DO-10 | 3 Sprint 2 | L1 Physical vs XBS (F30) | Compare count vs locked snapshot; attach RIs in order TIMING, LOCATION, CORRECTION-PENDING, UNIT-RULE, PACKING, PROVISIONAL, THIRD-PARTY, REMNANT; raise EX01/EX02. |  | 2026-10-27 | 2026-10-29 | 3 | DO-09 | L1 engine | Worked example KCS7948 gives residual 0 | 4.4, 8.3 | Not started
DO-13 | 3 Sprint 2 | F20 daily rules EX05–EX20 + upsert child flow | Rule child flows return (rule, key, qty, details); upsert on alternate key; auto-close when cleared. | Jones Alukwe | 2026-10-28 | 2026-11-04 | 6 | DO-08 | F20 + rules | Each EX code fires and auto-closes on test data | 8.5, 12.3 | Not started
DO-11 | 3 Sprint 2 | L2 XBS vs Comtras | SNI add-back, provisional, registers; RIs DOWNGRADE, PURCHASE-PENDING, WRONG-BASKET, ROLLOVER, BRIC-PENDING, SHORT-DELIVERY; EX15. | Nicole Akinyi | 2026-10-29 | 2026-11-03 | 4 | DO-10 | L2 engine | T4 passes on test data | 4.5 | Not started
DO-15 | 4 SIT | Load October month-end snapshots into UAT and lock | Day 1 feeds (Sun 1 Nov) loaded and locked; stock take created. | Andrew Tanui | 2026-11-02 | 2026-11-02 | 1 | DO-08, MO-09 | Locked snapshot | Wizard pre-checks all green | 5.2 | Not started
DO-12 | 3 Sprint 2 | L3 Baskets vs Contracts | Basket balances vs contract open quantities incl. roll-over lineage. |  | 2026-11-02 | 2026-11-04 | 3 | DO-11 | L3 engine | T5 passes | 4.6 | Not started
DO-17 | 4 SIT | Tie-outs T1–T8 and T10 | Completeness, mapping coverage, L1, L2, L3, mass balance, repeatability, timeliness; evidence in Git /test. | Nicole Akinyi | 2026-11-02 | 2026-11-06 | 5 | DO-12 | Tie-out evidence | All = 0 difference | 18.2 | Not started
DO-14 | 3 Sprint 2 | F23 provisional auto-match, F28 correction posting check | Close provisional on matching XBS receipt; mark corrections Posted from next snapshot or raise EX13. |  | 2026-11-03 | 2026-11-05 | 3 | DO-11 | Flows F23, F28 | Test receipt closes provisional; unposted correction ages to EX13 | 12.2 | Not started
DO-16 | 4 SIT | Run L1–L3 on October data and reconcile | Close count → L1; L2/L3 on month-end feeds; work residual with Finance/Ops. | Nicole Akinyi | 2026-11-04 | 2026-11-06 | 3 | WI-11 | Recon results | Residual explained to 0 or items listed | 4, 18.2 | Not started
DO-18 | 6 UAT | Fix UAT defects — intake and engine | Fix and redeploy within severity SLA. |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started
DO-19 | 7 Cutover | PROD master-data load and tie-out | Load and tie out all master data; mapping coverage = 100%. | Nicole Akinyi | 2026-11-24 | 2026-11-25 | 2 | MO-16 | PROD master data | T1/T2 pass in PROD | 20.1 | Not started
DO-20 | 7 Cutover | Switch feeds to PROD mailbox; 3 clean intake days | Owners send to PROD; monitor 25, 26, 27 Nov. |  | 2026-11-25 | 2026-11-27 | 3 | DO-19 | Clean intake log | 3 consecutive clean days | 20.1 | Not started
DO-21 | 7 Cutover | Opening baseline calculation | Agree last reconciled position (October parallel run); record historic unexplained as RI-BASELINE. | Nicole Akinyi | 2026-11-26 | 2026-12-02 | 5 | DO-16 | Baseline workbook | Approved by Finance + Ops | 4.8, 20.3 | Not started
DO-22 | 8 Hypercare | November L1–L3 runs; drive residual to 0 | Support Finance/Ops to clear exceptions and corrections by WD7 (Wed 9 Dec). | Nicole Akinyi, Jones Alukwe | 2026-12-03 | 2026-12-09 | 5 | PM-61 | Recon results | Residual 0 at all levels | 4, 5.2 | Not started
DO-23 | 8 Hypercare | Runbooks for intake and engine failures | One runbook entry per failure type. |  | 2026-12-07 | 2026-12-09 | 3 |  | Runbooks | Reviewed by Moses | 17 NFR-10 | Not started
Tasks where Denis is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-02 | 0 Discovery | Discovery sessions: Finance, Warehouse & Operations, Trade & QC, Logistics | Daphne Okwaro | 2026-10-02 | 2026-10-08
PM-15 | 1 Design | Formal data-feed request to XBS and Comtras/BRIC owners | Daphne Okwaro | 2026-10-12 | 2026-10-14
MO-01 | 1 Design | Inventory the ITB (John Nyongesa) solution | Moses Masibo | 2026-10-12 | 2026-10-13
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
NI-01 | 1 Design | Profile sample files from every feed | Nicole Akinyi | 2026-10-13 | 2026-10-16
MO-06 | 1 Design | Data-model review (34 tables, keys, alternate keys) | Moses Masibo | 2026-10-14 | 2026-10-16
MO-07 | 2 Sprint 1 | Shared mailbox and SharePoint STK-Intake site | Moses Masibo | 2026-10-15 | 2026-10-16
NI-02 | 2 Sprint 1 | Mapping coverage analysis | Nicole Akinyi | 2026-10-15 | 2026-10-21
WI-05 | 2 Sprint 1 | S5 Capture screen | William Imo | 2026-10-21 | 2026-10-23
AN-04 | 2 Sprint 1 | Stock take wizard (5 steps) + F10 notify | Andrew Tanui | 2026-10-21 | 2026-10-26
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
JO-06 | 3 Sprint 2 | Reconciliation workspace (custom page) | Jones Alukwe | 2026-10-28 | 2026-11-03
MO-10 | 3 Sprint 2 | Engine design review | Moses Masibo | 2026-10-28 | 2026-10-29
AN-07 | 3 Sprint 2 | F13 location variance check, recount and unidentified queues | Andrew Tanui | 2026-10-29 | 2026-10-30
AN-08 | 3 Sprint 2 | Variance review, manual approvals, close count + F14 | Andrew Tanui | 2026-11-02 | 2026-11-03
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11
MO-18 | 8 Hypercare | Knowledge transfer to NKG IT (2 × 2 h) | Moses Masibo | 2026-12-07 | 2026-12-09

## Nicole
Nicole Akinyi — Data Analyst
Owns: Data profiling, mapping coverage, test data, Power BI model and reports, month-end pack, parallel-run analysis. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
NI-01 | 1 Design | Profile sample files from every feed | For each file: row counts, keys, duplicates, blanks, grade/quality codes, units, date formats; compare to Appendix E templates. | Denis Otieno | 2026-10-13 | 2026-10-16 | 4 | PM-15 | Profiling report | Issues list sent to data owners | 7.2, App. E | Not started
NI-02 | 2 Sprint 1 | Mapping coverage analysis | Outturn → grade → secondary → primary basket; list unmapped and conflicting outturns for Trade/QC with eq60 impact. | Denis Otieno | 2026-10-15 | 2026-10-21 | 4 | NI-01 | Coverage report + unmapped list | List sent to Trade and QC | 8.2, 11.2 | Not started
NI-03 | 2 Sprint 1 | Build test data sets | Scenarios for every RI code and EX01–EX20: found-elsewhere, pockets, lights, timing, third-party, SNI, provisional, wrong basket, roll-over. | Frankie Omasaja | 2026-10-19 | 2026-10-23 | 4 | DO-02 | Test data pack in Git /test | Each scenario has expected result | 8.4, 8.5, 18 | Not started
NI-04 | 3 Sprint 2 | Power BI model | Dataverse connection; FactStock, FactRecon, FactException, FactMovement; dims; Import + DirectQuery split. |  | 2026-10-26 | 2026-10-28 | 3 | DO-03 | PBIP in Git | Model refreshes in DEV workspace | 13.1 | Not started
NI-05 | 3 Sprint 2 | DAX measures | Eq60 by source, Raw Diff, RI Total, Corrections, Residual, Residual OK, Count Accuracy %, Open/Overdue exceptions. |  | 2026-10-28 | 2026-10-29 | 2 | NI-04 | Measures | Measures match hand-calculated test values | 13.2 | Not started
NI-06 | 3 Sprint 2 | Eight report pages | Executive, Stock position, Reconciliation waterfall, Exceptions, Count performance, Provisional & SNI, Third parties, Data quality. |  | 2026-10-29 | 2026-11-04 | 5 | NI-05 | Report | Matches mockup 08; reviewed by PM | 13.3 | Not started
NI-08 | 3 Sprint 2 | Month-end pack template (F32) | Paginated report / Word template: residuals, waterfall, exceptions, corrections, sign-off history. | Jones Alukwe | 2026-11-03 | 2026-11-06 | 4 | NI-06 | Pack template | PDF generated from test period | 12.2 | Not started
NI-07 | 3 Sprint 2 | RLS, workspace app, embed | RLS by department/warehouse; publish workspace app "NKG EA Stock Control"; embed in Control Centre with Jones. | Jones Alukwe | 2026-11-04 | 2026-11-05 | 2 | NI-06 | Workspace app | Role test: Logistics sees only Logistics pages | 13.3 | Not started
NI-09 | 4 SIT | Parallel-run comparison report | Compare manual vs new solution: variances found, explanations, time taken (T9). | Daphne Okwaro | 2026-11-04 | 2026-11-06 | 3 | DO-16 | Comparison report | Shared with NKG sponsors | 18.2 T9 | Not started
NI-10 | 4 SIT | T7 report vs source tie-out | Every Power BI total vs Dataverse query total. |  | 2026-11-05 | 2026-11-06 | 2 | NI-06 | T7 evidence | 0 difference | 18.2 | Not started
NI-11 | 5 Training | Data dictionary | Generate from Dataverse; add business definitions. |  | 2026-11-09 | 2026-11-12 | 4 | DO-03 | Data dictionary | Published in STK-Knowledge | 21 | Not started
NI-12 | 6 UAT | Fix UAT defects — Power BI and pack | Fix and republish. |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started
Tasks where Nicole is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-02 | 0 Discovery | Discovery sessions: Finance, Warehouse & Operations, Trade & QC, Logistics | Daphne Okwaro | 2026-10-02 | 2026-10-08
PM-03 | 0 Discovery | BRD V1.1 (red = items to confirm) | Daphne Okwaro | 2026-10-05 | 2026-10-09
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
DO-02 | 1 Design | Finalise intake file templates and column mappings | Denis Otieno | 2026-10-14 | 2026-10-16
FR-02 | 2 Sprint 1 | Write SIT scripts | Frankie Omasaja | 2026-10-19 | 2026-10-23
DO-05 | 2 Sprint 1 | F02 Validate file (V1–V7) | Denis Otieno | 2026-10-21 | 2026-10-23
DO-07 | 2 Sprint 1 | Master-data migration | Denis Otieno | 2026-10-21 | 2026-10-23
JO-03 | 2 Sprint 1 | Mapping BPF + F22 + versioning | Jones Alukwe | 2026-10-21 | 2026-10-23
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
FR-03 | 4 SIT | Execute SIT scripts (rolling as features land) | Frankie Omasaja | 2026-10-26 | 2026-11-06
DO-11 | 3 Sprint 2 | L2 XBS vs Comtras | Denis Otieno | 2026-10-29 | 2026-11-03
JO-10 | 3 Sprint 2 | Stock Assistant set-up + topics T1–T5 | Jones Alukwe | 2026-11-02 | 2026-11-06
DO-17 | 4 SIT | Tie-outs T1–T8 and T10 | Denis Otieno | 2026-11-02 | 2026-11-06
JO-08 | 3 Sprint 2 | Downgrade worksheet + F25; SNI/shorts views; feedback log | Jones Alukwe | 2026-11-03 | 2026-11-04
JO-09 | 3 Sprint 2 | Sign-off BPF + F31 gate/lock + F32 trigger | Jones Alukwe | 2026-11-04 | 2026-11-06
DO-16 | 4 SIT | Run L1–L3 on October data and reconcile | Denis Otieno | 2026-11-04 | 2026-11-06
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
JO-11 | 5 Training | Topics T6–T10 + evaluation set | Jones Alukwe | 2026-11-09 | 2026-11-11
JO-13 | 5 Training | Train Trade, QC, Logistics, Finance, Management (Control Centre + Copilot) | Jones Alukwe | 2026-11-11 | 2026-11-13
DO-19 | 7 Cutover | PROD master-data load and tie-out | Denis Otieno | 2026-11-24 | 2026-11-25
DO-21 | 7 Cutover | Opening baseline calculation | Denis Otieno | 2026-11-26 | 2026-12-02
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11
DO-22 | 8 Hypercare | November L1–L3 runs; drive residual to 0 | Denis Otieno | 2026-12-03 | 2026-12-09

## William
William Imo — Power Apps Developer
Owns: Stock Take app (counter phone/tablet app), offline sync, count flows F11–F12, counter training. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
WI-01 | 1 Design | Review ITB Stock Take app | Walk every screen and formula; note delegation warnings, performance, what to keep/rebuild. |  | 2026-10-12 | 2026-10-13 | 2 | PM-05 | Review notes | Shared at stand-up | 9 | Not started
WI-02 | 1 Design | Shared component library (NKG theme) | Header, buttons, chips, tiles, input fields in NKG Green #006330 palette; published as component library for all canvas apps. | Andrew Tanui | 2026-10-13 | 2026-10-14 | 2 | MO-04 | Component library | Used by Stock Take app and Hub | 9.1 | Not started
WI-03 | 2 Sprint 1 | S1 Sign-in/version check and S2 Home | SSO, role & warehouse load, App.MinVersion check; Home tiles, banner with cut-off and time left. |  | 2026-10-15 | 2026-10-16 | 2 | WI-02 | Screens S1–S2 | Demoed at stand-up | 9.2 | Not started
WI-04 | 2 Sprint 1 | S3 My Assignments and S4 Location (QR) | Assignments grouped by zone with status chips; QR scan or pick; Start count / Mark empty / Cannot access (reason). |  | 2026-10-19 | 2026-10-22 | 3 | WI-03, DO-03 | Screens S3–S4 | QR test labels scan on 2 devices | 9.2 | Not started
WI-05 | 2 Sprint 1 | S5 Capture screen | Outturn scan/search (StartsWith, delegable); Expected / Found elsewhere / Not in list / Unidentified (photo); grade from mapping; packing default; bags + pocket; live Units/Kg/Eq60; category. | Denis Otieno | 2026-10-21 | 2026-10-23 | 3 | WI-04 | Screen S5 | AC-9.2: 20 test lines equal engine calculation | 9.3 | Not started
WI-06 | 3 Sprint 2 | S6 Location summary and close; F11 bulk submit | Review lines, totals, edit before submit, close location; F11 for >50 lines. |  | 2026-10-26 | 2026-10-27 | 2 | WI-05 | S6 + F11 | Close writes lines and status in one action | 9.4 | Not started
WI-07 | 3 Sprint 2 | Offline queue and sync (S9) | LoadData/SaveData queue; 30-s timer sync; Failed state with reason; idempotent on stk_localid. | Moses Masibo | 2026-10-27 | 2026-10-29 | 3 | WI-06 | Offline sync | AC-9.3: 100 offline lines sync with 0 duplicates, 0 loss | 9.5 | Not started
WI-08 | 3 Sprint 2 | Smart warnings + F12 not-in-list alert | Duplicate in location, counted elsewhere, implausible qty, pocket ≥ bag, closed location; F12 supervisor alert with photo. |  | 2026-10-28 | 2026-10-30 | 3 | WI-05 | Warnings + F12 | Each warning shown with test data | 9.3.3 | Not started
WI-09 | 3 Sprint 2 | S7 Recount (double-blind), S8 100% issue/receive, S10 Help | Recount task view; issue/receive during count; Help with rules card and Stock Assistant link. |  | 2026-10-29 | 2026-11-02 | 3 | WI-08 | Screens S7, S8, S10 | Recount goes to a different counter | 9.2 | Not started
WI-11 | 4 SIT | Floor support during parallel count | On the floor with counters; capture issues; quick fixes. | Andrew Tanui | 2026-11-02 | 2026-11-04 | 3 | DO-15 | Issue list | Count completed in new app | — | Not started
WI-10 | 3 Sprint 2 | Device and floor testing | Test on NKG phones/tablets — models to confirm in far zones and Wi-Fi dead spots; glove test; font sizes. | Frankie Omasaja | 2026-11-03 | 2026-11-05 | 3 | WI-07 | Device test report | No blocker on any device | 9.1 | Not started
WI-12 | 5 Training | Train counters and supervisors (Stock Take app) | 30-min hands-on per group + card; supervisor 1 h. | Andrew Tanui | 2026-11-09 | 2026-11-11 | 3 | FR-04 | Attendance | All named counters trained | 21 | Not started
WI-13 | 6 UAT | Fix UAT defects — Stock Take app | Fix and redeploy within severity SLA. |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started
Tasks where William is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
PM-13 | 1 Design | Design walkthrough with NKG (mockups + zero-variance model) | Daphne Okwaro | 2026-10-13 | 2026-10-13
AN-03 | 2 Sprint 1 | Location generator + QR labels | Andrew Tanui | 2026-10-21 | 2026-10-22
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
PM-31 | 4 SIT | Plan October month-end parallel run | Daphne Okwaro | 2026-10-26 | 2026-10-30
AN-11 | 4 SIT | Print and fix QR labels on bays for parallel run | Andrew Tanui | 2026-10-29 | 2026-10-30
FR-04 | 5 Training | User guides and quick reference cards | Frankie Omasaja | 2026-11-02 | 2026-11-10
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11

## Andrew
Andrew Tanui — Power Apps Developer
Owns: Stock Management Hub (plan, run, review, close, third parties, registers, admin), Hub flows. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
AN-01 | 1 Design | Review ITB Stock Management app | Admin, Import, Dashboard, Reports, Stock Takes approvals: document logic and data sources. |  | 2026-10-12 | 2026-10-13 | 2 | PM-05 | Review notes | Shared at stand-up | 10 | Not started
AN-02 | 2 Sprint 1 | Admin screens | Warehouses, grades, packing types, unit rules (with approval), stk_config editor with change reason, users and roles. |  | 2026-10-15 | 2026-10-19 | 3 | WI-02, DO-03 | Admin area | Config change writes audit record | 10.8 | Not started
AN-03 | 2 Sprint 1 | Location generator + QR labels | Generate A01–G14 per warehouse; deactivate not delete; print QR label sheet (PDF via Word template flow). | William Imo | 2026-10-21 | 2026-10-22 | 2 | AN-02 | Generator + label PDF | 98 labels generated for Main Warehouse test | 10.8 | Not started
AN-04 | 2 Sprint 1 | Stock take wizard (5 steps) + F10 notify | Type, cut-off, locked snapshot, scope, counters, review & create; pre-checks (feeds, lock, EX20, mapping); creates stocktake, assignments, hidden expected lines; F10 Teams/email. | Denis Otieno | 2026-10-21 | 2026-10-26 | 4 | AN-03, DO-06 | Wizard + F10 | Stock take created from test snapshot; counters notified | 10.2 | Not started
AN-05 | 3 Sprint 2 | Assignments board and auto-balance | Assign by zone; auto-balance by expected line count; block self-recount. |  | 2026-10-26 | 2026-10-27 | 2 | AN-04 | Assignments board | Balanced split for 98 locations | 10.2 | Not started
AN-06 | 3 Sprint 2 | Live monitor | KPIs, floor map, progress by counter, in-XBS-not-counted, counted-not-in-XBS; 60-s refresh. |  | 2026-10-27 | 2026-10-29 | 3 | AN-05, WI-06 | Live monitor | AC-9.4: new line visible within 60 s | 10.3 | Not started
AN-07 | 3 Sprint 2 | F13 location variance check, recount and unidentified queues | Compare with hidden expected; out of tolerance → recount to different counter; supervisor queues. | Denis Otieno | 2026-10-29 | 2026-10-30 | 2 | AN-06 | F13 + queues | Out-of-tolerance location creates recount | 10.4, 12.2 | Not started
AN-11 | 4 SIT | Print and fix QR labels on bays for parallel run | Generate and print labels; fix on bays with warehouse team. | William Imo | 2026-10-29 | 2026-10-30 | 2 | AN-03 | Labels on bays | All bays in scope labelled | 10.8 | Not started
AN-08 | 3 Sprint 2 | Variance review, manual approvals, close count + F14 | Supervisor actions with comment; close only when all closed/recounts done; F14 freezes lines and triggers L1. | Denis Otieno | 2026-11-02 | 2026-11-03 | 2 | AN-07, DO-10 | Review + close | AC-9.5: close to L1 with no manual step | 10.4–10.5 | Not started
AN-09 | 3 Sprint 2 | Third-party confirmations + F15 | Balance statements M−5, capture replies, chase M−3, escalate M−2, EX10/EX11. |  | 2026-11-04 | 2026-11-05 | 2 | DO-13 | Screen + F15 | Test third party with difference creates RI-THIRD-PARTY | 10.6 | Not started
AN-10 | 3 Sprint 2 | Registers + F24, Imports & load log, Audit | Disputed, franchise, ex-office, sweepings, loose bags, lights; release actions; upload-to-Incoming fallback; audit view. |  | 2026-11-05 | 2026-11-06 | 2 | AN-09 | Screens + F24 | Release creates correction where required | 10.7, 10.9 | Not started
AN-12 | 5 Training | Train Operations admin and warehouse managers (Hub) | 2-h session: wizard, monitor, recounts, close, registers, third parties, admin. |  | 2026-11-10 | 2026-11-11 | 2 | FR-04 | Attendance | Trained users can create a stock take unaided | 21 | Not started
AN-13 | 6 UAT | Fix UAT defects — Hub | Fix and redeploy within severity SLA. |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started
Tasks where Andrew is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
PM-13 | 1 Design | Design walkthrough with NKG (mockups + zero-variance model) | Daphne Okwaro | 2026-10-13 | 2026-10-13
WI-02 | 1 Design | Shared component library (NKG theme) | William Imo | 2026-10-13 | 2026-10-14
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
PM-31 | 4 SIT | Plan October month-end parallel run | Daphne Okwaro | 2026-10-26 | 2026-10-30
DO-15 | 4 SIT | Load October month-end snapshots into UAT and lock | Denis Otieno | 2026-11-02 | 2026-11-02
WI-11 | 4 SIT | Floor support during parallel count | William Imo | 2026-11-02 | 2026-11-04
FR-04 | 5 Training | User guides and quick reference cards | Frankie Omasaja | 2026-11-02 | 2026-11-10
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
WI-12 | 5 Training | Train counters and supervisors (Stock Take app) | William Imo | 2026-11-09 | 2026-11-11
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11

## Jones
Jones Alukwe — Power Apps Developer / Copilot Developer
Owns: Stock Control Centre (model-driven), BPFs, exceptions, corrections, sign-off gate, Copilot Stock Assistant. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
JO-01 | 1 Design | Copilot Studio and model-driven readiness check | Check Copilot Studio availability/licensing in tenant; list knowledge sources; draft model-driven site map. | Moses Masibo | 2026-10-12 | 2026-10-13 | 2 | PM-16 | Readiness note | Input to OD8 | 11, 14 | Not started
JO-02 | 2 Sprint 1 | Model-driven app shell | Site map (Master data, Stock positions, Reconciliation, Exceptions, Close, Insights); main forms and views for master-data tables. |  | 2026-10-15 | 2026-10-19 | 3 | DO-03 | App shell | All tables navigable | 11.1 | Not started
JO-03 | 2 Sprint 1 | Mapping BPF + F22 + versioning | Proposed → QC verified → Finance approved → Active; effective dates; coverage and conflict views; F22 notifications; overlap blocked. | Nicole Akinyi | 2026-10-21 | 2026-10-23 | 3 | JO-02 | Mapping BPF | UAT-03 path works end to end in DEV | 11.2 | Not started
JO-04 | 3 Sprint 2 | Contracts lineage + F26, provisional pipeline views | Contract form with allocations, relief, amendments; roll-over lineage; provisional stages and ageing. |  | 2026-10-26 | 2026-10-27 | 2 | JO-02 | Forms + F26 | Roll-over test links successor contract | 11.4–11.5 | Not started
JO-05 | 3 Sprint 2 | Exception register + F21 notifications | Views (my, team, overdue, closed); SLA timer; comments table; resolution codes; F21 owner alerts, 16:00 reminders, escalation. |  | 2026-10-27 | 2026-10-29 | 3 | DO-13 | Register + F21 | Overdue test exception escalates to manager | 11.8 | Not started
JO-06 | 3 Sprint 2 | Reconciliation workspace (custom page) | Tabs L1/L2/L3; tiles raw/RIs/corrections/residual; drill grid; side panel (RIs, exceptions, comments); Attach RI, Propose correction, Re-run. | Denis Otieno | 2026-10-28 | 2026-11-03 | 5 | DO-10 | Workspace | Matches mockup 04 with live DEV data | 11.6 | Not started
JO-07 | 3 Sprint 2 | Corrections + approval matrix + F27 batch | Correction form, SoD (proposer ≠ approver), approval by type/value, weekly Excel batch per system owner. |  | 2026-11-02 | 2026-11-03 | 2 | JO-05 | Corrections + F27 | Same-user approval is blocked | 11.9, 15.2 | Not started
JO-10 | 3 Sprint 2 | Stock Assistant set-up + topics T1–T5 | Agent in DEV, Entra auth, STK-Knowledge library, read-only actions; topics: where is outturn, why variance, count progress, my exceptions, explain a rule. | Nicole Akinyi | 2026-11-02 | 2026-11-06 | 5 | JO-01, DO-10 | Agent with T1–T5 | T1–T5 answer test questions correctly | 14 | Not started
JO-08 | 3 Sprint 2 | Downgrade worksheet + F25; SNI/shorts views; feedback log | Monthly Low Grade candidates; approval creates mapping versions + basket-transfer correction. | Nicole Akinyi | 2026-11-03 | 2026-11-04 | 2 | JO-03 | Worksheet + views | Approved downgrade shows RI-DOWNGRADE in L2 | 11.3, 11.7, 11.10 | Not started
JO-09 | 3 Sprint 2 | Sign-off BPF + F31 gate/lock + F32 trigger | Six stages with automatic gate checks; final locks period and publishes pack. | Nicole Akinyi | 2026-11-04 | 2026-11-06 | 3 | JO-06, NI-08 | Sign-off BPF | UAT-06: sign-off blocked while residual ≠ 0 | 11.11 | Not started
JO-11 | 5 Training | Topics T6–T10 + evaluation set | Contract status, provisional status, summarise comments, draft correction note, month-end readiness; run ~30-question evaluation built with Nicole. | Nicole Akinyi | 2026-11-09 | 2026-11-11 | 3 | JO-10, NI-09 | Agent T1–T10 + eval results | ≥ 90% correct; 100% on numbers | 14.4 | Not started
JO-13 | 5 Training | Train Trade, QC, Logistics, Finance, Management (Control Centre + Copilot) | 1.5–2 h per group: mapping, downgrade, provisional, SNI, exceptions, corrections, workspace, sign-off, Copilot. | Nicole Akinyi, Daphne Okwaro | 2026-11-11 | 2026-11-13 | 3 | FR-04 | Attendance | ≥ 90% of named users trained | 21 | Not started
JO-12 | 5 Training | Publish Stock Assistant to Teams (UAT) | Teams channel publish; Control Centre side pane; Help link in app. | Moses Masibo | 2026-11-12 | 2026-11-13 | 2 | JO-11 | Published agent | Available to UAT users | 14 | Not started
JO-14 | 6 UAT | Fix UAT defects — Control Centre + Copilot | Fix and redeploy within severity SLA. |  | 2026-11-16 | 2026-11-26 | 9 | PM-50 | Fixes | No open Sev 1/2 | — | Not started
Tasks where Jones is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
PM-13 | 1 Design | Design walkthrough with NKG (mockups + zero-variance model) | Daphne Okwaro | 2026-10-13 | 2026-10-13
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
DO-13 | 3 Sprint 2 | F20 daily rules EX05–EX20 + upsert child flow | Denis Otieno | 2026-10-28 | 2026-11-04
FR-04 | 5 Training | User guides and quick reference cards | Frankie Omasaja | 2026-11-02 | 2026-11-10
NI-08 | 3 Sprint 2 | Month-end pack template (F32) | Nicole Akinyi | 2026-11-03 | 2026-11-06
NI-07 | 3 Sprint 2 | RLS, workspace app, embed | Nicole Akinyi | 2026-11-04 | 2026-11-05
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11
DO-22 | 8 Hypercare | November L1–L3 runs; drive residual to 0 | Denis Otieno | 2026-12-03 | 2026-12-09
PM-62 | 8 Hypercare | First live sign-off (residual = 0 gate) | Daphne Okwaro | 2026-12-09 | 2026-12-09

## Frankie
Frankie Omasaja — QA / Test & Documentation — role to confirm
Owns: SIT scripts and execution, defect log, UAT scripts, user guides and training material formatting. Live links to Master Plan — update status there.
ID | Phase | Task | Detailed description / steps | Support | Start | End | Work days | Depends on | Deliverable | Done when | Spec ref | Status | Overdue?
FR-01 | 1 Design | Test strategy and defect process | Defect log (severity 1–4, owner, status), test case template, SIT script structure per area. | Daphne Okwaro | 2026-10-13 | 2026-10-16 | 4 | PM-04 | Test strategy + defect log | Approved by PM | 18 | Not started
FR-02 | 2 Sprint 1 | Write SIT scripts | Scripts for INT, MAP, CNT, EXC, COR, PRV, REG, 3P, CON, FB areas with steps, test data and expected results. | Nicole Akinyi | 2026-10-19 | 2026-10-23 | 4 | FR-01, NI-03 | SIT script pack | Reviewed by Moses | 18.1, App. B | Not started
FR-03 | 4 SIT | Execute SIT scripts (rolling as features land) | Run scripts per area as each feature is merged; log defects; retest fixes. | Nicole Akinyi | 2026-10-26 | 2026-11-06 | 10 | FR-02 | SIT results + defect log | All scripts executed; 0 open Sev 1/2 | 18 | Not started
FR-04 | 5 Training | User guides and quick reference cards | Counter card (laminated), supervisor, Ops admin, Trade/QC/Logistics, Finance/Management guides from developer inputs. | William Imo, Andrew Tanui, Jones Alukwe | 2026-11-02 | 2026-11-10 | 7 | PM-32 | Guides + cards | Reviewed by PM | 21 | Not started
FR-05 | 5 Training | UAT scripts and UAT participant packs | Scenarios UAT-01..07 per department with test data and sign-off sheet. | Daphne Okwaro | 2026-11-09 | 2026-11-13 | 5 | PM-32 | UAT pack | Reviewed by department leads | 18.3 | Not started
FR-06 | 8 Hypercare | As-built documentation pack | Spec as-built, admin guide, user guides, runbooks, data dictionary in STK-Knowledge. | Moses Masibo | 2026-12-07 | 2026-12-11 | 5 |  | Handover pack | Accepted by NKG IT | 20.4 | Not started
Tasks where Frankie is supporting
ID | Phase | Task | Owner | Start | End
PM-01 | 0 Discovery | Project kick-off and warehouse walk-through | Daphne Okwaro | 2026-10-01 | 2026-10-01
PM-20 | 2 Sprint 1 | Sprint 1 planning | Daphne Okwaro | 2026-10-12 | 2026-10-12
NI-03 | 2 Sprint 1 | Build test data sets | Nicole Akinyi | 2026-10-19 | 2026-10-23
PM-21 | 2 Sprint 1 | Sprint 1 review / demo to NKG | Daphne Okwaro | 2026-10-23 | 2026-10-23
PM-30 | 3 Sprint 2 | Sprint 2 planning | Daphne Okwaro | 2026-10-26 | 2026-10-26
PM-40 | 5 Training | Training plan, schedule and invites | Daphne Okwaro | 2026-10-29 | 2026-11-06
WI-10 | 3 Sprint 2 | Device and floor testing | William Imo | 2026-11-03 | 2026-11-05
MO-13 | 4 SIT | Performance and security tests | Moses Masibo | 2026-11-03 | 2026-11-06
PM-32 | 4 SIT | Sprint 2 review / SIT exit | Daphne Okwaro | 2026-11-06 | 2026-11-06
PM-50 | 6 UAT | Run UAT and daily defect triage | Daphne Okwaro | 2026-11-16 | 2026-11-27
PM-61 | 7 Cutover | First live month-end count (November) in PROD | Daphne Okwaro | 2026-12-01 | 2026-12-03
PM-63 | 8 Hypercare | Hypercare: daily stand-up with NKG super users | Daphne Okwaro | 2026-12-01 | 2026-12-11

## Holidays
Public holidays used in working-day counts
Kenya. Verify against the gazette notice; add any new holiday here and all day counts update.
Date | Holiday | Note
2026-10-20 | Mashujaa Day | Tuesday — inside Sprint 1
2026-12-12 | Jamhuri Day | Saturday in 2026
2026-12-25 | Christmas Day | After project end
2026-12-26 | Boxing Day | After project end